Subcontractor:  Bombard Mechanical, LLC

Scopes:  HVAC Systems & Plumbing Systems

Project:  Tonopah HS Field Replacement

Date:  5/18/26

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Michael Ruesch | CORE Construction | MEP |  |
| 8. | Brian Qualls | Bombard Mech. | Estimator |  |
| 9. | Brent Vondrak | Bombard Mech. | Estimator |  |
| 10. | Nathan Ruesch | Bombard Mech. | Cx Manager |  |

SCOPE

Plumbing:

- Review the Scope Narrative and subcontractors proposal

  - Domestic water balance – Bombard to check to see if this is included in TAB number provided.

  - Safe off of existing building – can include up to 15-20 feet away from the building

  - Equipment and fixtures per schedules provided

  - Includes supply of access panels (7) to be installed by others

  - Includes sealing all penetrations

  - Condensate piping is included. Included insulation on condensate piping

  - Haul off of spoils – not included but will store at designated locations

  - Hard dig costs – not included. CORE requests Bombard to assume hard dig for UG plumbing work. Provide added cost.

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

  - Heat trace – for hot water room only (may not be needed with small design change)

  - Exterior hose bibs – assumed two locations (outside of family RR and outside of gang restroom)

  - Alternate #A:

    - Demo Wet Utilities at existing school:

      - Included removal of fixtures, cut and cap 2 feet down, and concrete patch back.

      - Included locations shown on drawings

  - Alternate #B:

    - New propane tank at existing school:

    - Include UG piping, above grade to connect to existing, and a concrete pad.

      - CORE requests added price for hot patch

      - Includes only one point of connection. CORE to review existing conditions more and let Bombard know if additional pricing is needed.

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

Mechanical:

- Review the Scope Narrative and subcontractors proposal

  - Included demo and safe off of existing concession building

  - Bombard included 2 sets of filters. CORE requests 4 sets of filters for the project.

  - All equipment is per the schedules

  - Bombard to check to see if low-ambient kit is included. If no, provide add.

  - Includes access panel for unit above hard lid.

  - Includes all dampers shown.

  - Duct heaters: controllers have to be added to tie into fan coil units.

    - Includes conduit and pathway for controls

  - CORE requested Bombard to look to see if there would be any impacts if we relocate the condensing unit over to NW corner of Team #2 room

  - Includes cutting of roof deck, and curb, for exhaust fan

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

  - Alternate #01: evacuate split systems refrigerant at existing school

    - Assumed up to 3 days of work for two guys

  - Alternate #02:

    - Combined package discount (award plumbing and HVAC): Deduct $5,000

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP end of July

  - Start for this scope: Demo starts in November

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| VRF & Exhaust Fans | 2 weeks | 8 weeks |  |  |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| UG Plumbing | 2-3 | 1 week |  |  |
| In wall & OH rough |  | 2-3 weeks |  |  |
| MP Trim |  | 1 week |  |  |
| Startup |  | Couple days |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- Apprentice Utilization Requirements