Subcontractor:  CG&B Enterprise Inc

Scopes:  Synthetic Turf

Project:  Tonopah HS Field Replacement

Date:  5/20/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Michelle Hall | CG&B | Bid Coordinator |  |
| 8. | Craig Edwards | CG&B | VP |  |
| 9. | Jeff Wasson | CG&B | Estimator |  |
| 10. | Tyrus |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Excludes Aco drain system

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

    - Includes 4” of type 2 base

      - Assume the field will not perk

      - Assume fractured rock to follow the detail

    - Includes nailer board

    - Includes 3rd generation (Hellas Matrix Helix 46oz) turf

    - Assumes base and turf from subgrade

    - Assumes turf install after paving but before track surfacing

    - Includes field signage

      - No issue with color

    - Assume water source is available

    - Assume 1/4” tolerance for base

    - Assume proposal is valid till NTP

    - Asumes 4/10 work week

- Alternates

  - Supply and install perf pipe drain.

- Value Engineering

- Mock Ups

- Weather Protection

  - No issues with weather during installation

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Base and Turf |  | 6-8 weeks |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Provide cost of 4th generation turf and product information

- Provide cost for athletic equipment package 019.

  - Excluded discus mix