Subcontractor:  Cheek Construction LLC

Scopes:  Concrete

Project:  Tonopah HS Field Replacement

Date: 5/20/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Tristen Mathisen | Cheek Construction | Estimator |  |
| 8. | Thomas | Cheek Construction | Estimator |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Did not include valley gutter at north end.

    - Excluded concrete washout

    - Excluded pole vault box

    - Excludes bollards

    - Excludes footings for discus cage

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

    - Flag pole footings and install included in the total

    - Includes footings under CMU walls

    - Includes excavation

    - Includes hard dig

    - Includes footings for bleachers, press box and score board

    - Assume 6” type 2 over 4” concrete flat work

    - Supply and install all type 2.

    - Assume 551 linear feet of the Acco slot drain (Half moon)

    - Assume 6” concrete around the slot drain

    - Includes ticket booth slab

    - Assume haul off of spoils

      - No decut for onsite spoils

    - Included prevailing wage and zone pay

    - Includes discus and shot put concrete pad

      - Will install equipment if provided

    - Includes long jump curb

    - Includes mow-curb

    - Includes light pole bases

    - Assumes 6”x6” mesh at flatwork

    - Assumes 6” space between pour and rip rap.

    - Included goal post footing

    - Includes backfilling footings

    - Assume saw cutting anything over 10ft wide

    - Assume getting concrete from Yerington

    - Assume 3 mobs

- Alternates

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Provide cost for 4 more footings at the press box

- Price all press box footings (8) as 6’x6’.

- Provide price for a thicken edge slab under the bleachers, 18” wide, 24” deep, and a 4” slab w/#4 18” O.C.

- Provide a breakout cost for the slab for the press box

- Provide cost for valley gutter on the north end. Per sheet G1.0

- Provide cost for the Acco slot drain around the entire field.

- Provide a deduction of the NDOT head wall

- Provide cost for the pole vault box install and concrete. (Box provided by others)

- Provide deduct for light pole bases

- Provide cost for 6” concrete in front of the concessions (north entrance) and by the gate

- Provide cost to remove and reinstall the visitor bleacher for new concrete

- Provide cost for concrete at the remaining visitor bleachers

- Provide cost for discus cage sleeves (6) 30” deep by 18” wide.

- Research a concrete batch plant from Pahrump (Robertson)

- Provide cost for 4 bollards at the electrical equipment