Subcontractor:  Elite Sport Builder

Scopes:  Running Track Surface

Project:  NCSD Tonopah HS Sports Field Replacement

Date:  5/14/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Troy Rudolph | Elite Sports Builders | President |  |
| 8. | Aaron Dry | Elite Sports Builders | Estimator |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Excluded athletic equipment

    - Excluded compliance testing for striping

    - Design team to clarify the level of testing for striping

  - Deviations from specifications

    - Surfacing is 13-14 mm

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

    - Wind will be an issue when spraying the track

  - Inclusions or assumptions to cover grey areas in the scope

    - Includes dumpsters

    - Needs the track to be uninterrupted by any animal/person

    - Assume to be the last contractor for surfacing

    - Assume 55 degrees at surface and air temperature

    - Includes 2nd tier striping sub

    - Includes long jump and shot put areas

    - Includes travel cost

    - Assume coordination meeting with paving for tolerances

    - Includes 300 sqft of paving patching not exceeding ½”

    - Includes masking for curb and fencing (Assume winds of 10-15 MPH)

    - Includes 11mm base mat

    - Assume 4/10 work weeks

    - Assume D 1/2” mix w/5.6-5.8% oil content and heavy fines

    - Assume aggregate fully washed or crushed

- Alternates

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Cure |  | 3-4 days |  |  |
| Striping |  | 1-2 days |  |  |
| Track surfacing |  | 20 days |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

- Prevailing wage

  - Included

HOMEWORK

- Confirm the cost of the stencil for lettering

- Confirm 5-year warranty

- Provide cost of OT for Friday and Saturday (Assume 4/10 work weeks)

- Send over specs for track