Subcontractor:  Foursquare

Scopes:  Metal Panels

Project:  Tonopha Field Replacement

Date:  5/19/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | LaMar Noorda | Foursquare | Project Manager |  |
| 8. | Garret Noorda | Foursquare | Estimator |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Excludes skylight

    - Excludes metal sheathing

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

    - Concerns of snow ripping off the gutter

  - Inclusions or assumptions to cover grey areas in the scope

    - Assumes framer to frame up to the eeve

    - Assumes berrage z lock standing seam roof

      - PBR to have cost savings if changed

      - CORE to clarify with the design team

    - Assumes continuous z lock clips

    - Assume the soffit panel at the high side of the roof

      - Assume waterproofing to end at the clip, not to wrap to the building

      - Excluded venting at the soffit

    - Includes penetrations

    - Assumes one downspout

    - Includes gutter attachment for added strength

    - Can add a 20-year warranty from Berrage for 3,500.

    - Includes vents and pass-throughs, assumes nothing lands on a rib.

      - Includes multiple trips for coordination

    - Includes a pass-through window

      - Assumes metal instead of wood for the countertop

- Alternates

  - Custom color $20,000 and 24-week lead time.

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| Metal roof |  | 3 weeks |  | Standard color |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Roofing |  | 5 days |  | Snow can cause delay |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Provide price for splash box.

- Provide price for metal signage and bulletin board.