CORE CONSTRUCTION

# Attachment A Index — PM Review Packet (v2)

Tonopah THS Sports Complex  ·  Nye County School District  ·  CMAR / GMP

Generated 2026-07-31 from 01-index/package-index-v2.json and companions. Every figure and quotation below is pulled from the artifacts, not retyped.

How to use this packet

- Part A gates everything else and takes minutes. Three structural decisions that shape all 33 exhibits.

- Part B is nine open decisions only you can settle, ranked by severity.

- Part C is a four-package content spot-check to confirm the verbatim parse is faithful.

- Part D lists what is known to be still missing, so nothing is hidden going into review.

The parts are ordered by leverage — stop wherever you like.

# Part A — Three structural decisions

These decide the shape of all 33 exhibits. Every option below is worked out using RFP-030 Concrete, so you are comparing actual output rather than choosing from a description.

## A1.  How scope items are stored

RFP-030’s scope doc contains 72 items across three sub-scopes (Site Concrete, Cast-in-Place Structural, General Requirements).

### Option 1 — Verbatim (what the index does today)

Every sentence stored exactly as written, unedited. Five of the 72:

Supply and install slot drain / trench drains and concrete curb along track perimeter and as indicated per detail D/L1.03, including all excavation, trenching, bedding, and backfill.

Includes all piping, radius slot drains, storm drain collector pipe, concrete encasements as required, cleanouts, and all storm water drainage structures as indicated and required for a complete slot drain storm drainage system.

Dowel all exterior sidewalks to the building slab at entrances and doorways, whether or not detailed on drawings.

Provide and install 5/8” diameter x 18” long slick dowels at 18-inches on center (minimum) at all cold joints, whether shown or not.

Athletic Equipment footings (including football goal posts, high jump posts, etc.) Coordinate with Track & Field Athletic Equipment Subcontractor for requirements.

Length: 72 lines.   Traceability: every line quotable back to the scope doc verbatim.

### Option 2 — Summarized

Same scope condensed to prose. This is RFP-030’s Site Concrete sub-scope written out from its 24 verbatim items, losing nothing material:

Site Concrete. Supply and place concrete and reinforcement for all site flatwork, athletic equipment pads, curbs, take-off boards, turndown edges, and associated concrete items, including layout. Concrete curbs at the Synthetic Turf Sports Field and Running Track. Slot/trench drains and concrete curb along the track perimeter per detail D/L1.03, including excavation, trenching, bedding, backfill, all piping, radius slot drains, storm drain collector pipe, concrete encasements, cleanouts, and storm water drainage structures — connection to the site storm drainage system by others. Equipment pads including transformer pad. Keyed, saw-cut, control and expansion joints with filler, sealants, and white cap; control joint layout shop drawings for architectural approval. Dowel exterior sidewalks to the building slab at all entrances and doorways whether or not detailed, and provide 5/8" x 18" slick dowels at 18" o.c. minimum at all cold joints whether shown or not. Cast-in-place footings for site items including overexcavation per the Geotechnical Report: scoreboard, pressbox, ticket booth slab-on-grade and footings, bleacher footings and grade beams, athletic equipment footings (football goal posts, high jump posts), and sports field light pole bases — coordinating requirements with each respective subcontractor. Sacking of exposed surfaces, drypack under light pole base plates, and installation of anchor bolts furnished by others (templates by Electrical). Install steel embeds and bollards supplied by others, with footings, concrete infill and domed tops. Supply Type II, prepare sub-base, place and compact.

Length: roughly one paragraph per sub-scope, so about 3 paragraphs instead of 72 lines.

What you give up: you can no longer cite one sentence and point at it in the scope doc. Merging sentences also blurs boundaries — note how "whether or not detailed on drawings" and "whether shown or not" now sit mid-paragraph, when verbatim they stand out as the deliberate catch-all provisions they are.

### Option 3 — Both

Verbatim retained in the index as the source of record; condensed prose generated into the exhibit. Costs nothing but a generation step — the exhibit reads cleaner while the index stays quotable.

DECIDE A1:

☐  Verbatim only        ☐  Summarized only        ☐  Both

## A2.  What gap/overlap QA is built on

### Option 1 — Coordination clauses (what I proposed)

RFP-030’s scope doc names 14 coordination clauses. Each names a counterparty, so each becomes a specific checkable question:

| RFP-030 says | Seam to check | Counterparty |
| --- | --- | --- |
| "Scoreboard footings. Coordinate with Scoreboard Subcontractor" | Does ITB-089 exclude its own footings? | ITB-089 |
| "Pressbox footings… Bleacher footings / grade beams" | Does RFP-094 exclude footings? | RFP-094 |
| "Prefabricated Ticket Booth slab-on-grade and footings" | Does RFP-109 exclude slab and footings? | RFP-109 |
| "Athletic Equipment footings (football goal posts, high jump posts)" | Does ITB-019 exclude footings? | ITB-019 |
| "installing anchor bolts furnished by others… templates supplied by Electrical" | Who furnishes vs installs? | RFP-103 |
| "Install all steel embeds (supplied by others)… all bollards" | Who supplies? | RFP-033 |
| "Coordinate required masonry laps… rebar safety caps" | Handoff point | RFP-031 |
| "sleeves in slab-on-grade" / "layout requirements" | Sleeve and layout responsibility | RFP-098, RFP-100, RFP-103 |

→  8 distinct counterparties, 8 concrete questions, each traceable to a sentence in the contract.

### Option 2 — CSI divisions

RFP-030 is Division 03 Concrete. Checking overlaps by division finds only two packages: ITB-067 Concrete Finishing, which claims Division 03, and RFP-031 Masonry, which lists it as related.

What it misses: every footing seam above. Scoreboard, bleachers, press box, ticket booth and athletic equipment are Division 11/13 items — their footings are Division 03, but a division-level check never pairs RFP-030 with ITB-089 or ITB-019, because those packages are not Div 03. Those footing seams are exactly where your rulings have already been needed twice.

### Option 3 — Both

Coordination clauses as the primary spine, CSI divisions as a secondary sweep to catch packages that share a division but never mention each other — which is how ITB-066 vs ITB-067 sealed concrete surfaced.

DECIDE A2:

☐  Coordination clauses        ☐  CSI divisions        ☐  Both

## A3.  How drawings get cited

RFP-030 today: 1 authoritative citation, 12 candidates.

### Option 1 — Conservative (what the index does today)

Only sheets the scope narrative names outright become citations. Cited: L1.03, because the scope doc says "per detail D/L1.03". Held as candidates: L1.00, L1.01, L1.06, A1-12, A1-20 ⚠, S0-00, S0-01, S1-30, S1-40, S2-10, S3-00, S3-01.

Risk: RFP-030’s exhibit would cite one landscape detail sheet and none of the structural foundation sheets — no S1-30 Scoreboard Foundation, no S1-40 Home Grand Stands, no S3-00/S3-01 Typical Foundation Sections. For a concrete package that is visibly too thin.

### Option 2 — Promote where the scope doc corroborates the content

Promote a candidate when the scope doc describes that work even without naming the sheet. Seven would become citations:

| Sheet | Scope doc language that corroborates it |
| --- | --- |
| S1-30 Foundation Plan – Scoreboard | "Scoreboard footings" |
| S1-40 Foundation Plan – Home Grand Stands | "Bleacher footings / grade beams" |
| S2-10 Foundation & Roof Framing – Concessions | "continuous footings, slab-on-grade, turned-down edges" |
| S3-00, S3-01 Typical Foundation Sections | "cast-in-place footings", "stepped footings at utility entrances" |
| S0-00 General Notes | "Class D Seismic Design Category; Importance Factor 1.0" |
| A1-20 Site Details ⚠ | "expansion joints… control joints" — must be re-read at ADD 1 revision |

Would stay candidates: L1.00, L1.01, L1.06 (landscape sheets, more likely RFP-016/RFP-022 territory), A1-12, S0-01.

### Option 3 — Promote all, flag the doubtful

All 12 become citations; the landscape sheets carry a "verify ownership" flag. Risk: RFP-030’s exhibit would cite three landscape construction sheets. If those belong to RFP-016 or RFP-022, you have handed the concrete sub drawings for someone else’s work — the exact assignment-from-drawings failure that got v1 rejected.

DECIDE A3:

☐  Conservative        ☐  Promote where corroborated        ☐  Promote all, flag doubtful

# Part B — Open decisions

Nine items only you can settle, ranked by severity.

B1   [HIGH]  Three packages have no specification from any source

ITB-008 Surveying, ITB-066 Fluid-Applied Flooring and RFP-109 Ticket Booth have no "Primary Specifications" section in their scope docs — verified against the source text, not a parsing artifact. The other 30 docs all have one. ITB-066 also has no matching CSI section in the spec manual, so it has no execution standard from any source. RFP-109’s substitute is the written spec block on sheet A1-40.

Decision needed: What governs execution for each?

B2   [HIGH]  "070 Final Cleaning" — four proposals, no package

CSI, Lady Lux and Nevada Angels (plus a Nevada Angels descope) bid a package numbered 070 Final Cleaning. No such package exists on either the 1% list or the ITB list. Final cleaning is the classic scope every trade assumes belongs to someone else.

Decision needed: Is this a 34th package, a CORE general-conditions scope, or folded into another package?

B3   [HIGH]  Prevailing wage — Clark County vs Nye County

Clarification No. 2 replaced the prevailing wage section in its entirety and directs bidders to CLARK County rates. The project sits in Nye County, and CLAUDE.md records the Southern Nevada Rural Region. This affects all 33 subcontracts as a direct cost and compliance item.

Decision needed: Which rate schedule governs?

B4   [MEDIUM]  "065 Sealed Concrete" straddles ITB-066 and ITB-067

Sealed concrete appears under filename numbers 065, 066, 067 and combined "066, 067". Both packages currently show the identical four bidders (FW Specialties, NRC, Ryerson, SI Legacy), and ITB-066 has no spec section.

Decision needed: Which package carries sealed concrete?

B5   [MEDIUM]  Supply-only vs install-only bids split several packages

ITB-019: Exerplay and SportsEdge bid SUPPLY, Great Western bid INSTALL. ITB-056: Hallgren SUPPLY, SNV Specialties INSTALL. RFP-094 and RFP-109 received SUPPLY-only proposals — but sheet A1-20’s Site Equipment Matrix designates Bleachers, Press Box and Ticket Booth as CFCI (contractor furnished, contractor installed), so those cannot be left supply-only.

Decision needed: For each split package, which package carries installation?

B6   [MEDIUM]  Procurement flags on proposals

15 proposals have no signed Bid Form, 5 are late, 2 bypassed Building Connected, 2 are marked DO NOT USE, and 1 is value-only with no scope detail (Conti, RFP-103). RFP-045’s awarded sub Foursquare carries both the no-Form and the bypassed-Building-Connected flags. NRS 338.16995 governs the 1% list, so this is a procurement process exposure rather than a paperwork gap.

Decision needed: Do any of these block subcontract execution?

B7   [MEDIUM]  32 91 13 leveling exposure on RFP-016

Your ruling put Section 32 91 13 Track & Field Event Inorganic Material Mix — the discus and shot put material — in RFP-016. BrightView/GTI’s scope review explicitly EXCLUDED "discuss and shot put pads". The awarded sub is Black Canyon.

Decision needed: Confirm Black Canyon carries 32 91 13.

B8   [LOW]  Addendum #1 change list disagrees with the revised drawing index

The addendum’s narrative §5.01 names five reissued sheets. The revised G0-00 drawing index marks seven, adding A2-10 and A10-30 — both of which carry real scope changes (locker re-layout, new filler keynote, restroom partition changes). A bidder working from the addendum text gets a different picture than one cross-checking the cover sheet.

Decision needed: Worth raising with KNIT? Should the subcontract state that G0-00’s index governs current revisions?

B9   [LOW]  Two project facts still unconfirmed

The CORE job number is recorded as "likely 25-10-003". The Precon→Ops handoff date, which starts the 30-day buy-out clock, is still TBD — which is why the Buy-Out Console shows TBD rather than a countdown.

Decision needed: Confirm both.

# Part C — Content spot-check

Four packages, chosen because they carry the most boundary surface or your recent rulings. For each, open the scope doc and confirm the index did not lose or distort anything.

## RFP-030 — Concrete

Open:  00-source-docs/02-trade-scopes-bidform/Scope of Work - 030 Concrete.docx

| Scope items captured | 72 (verbatim) |
| --- | --- |
| Coordination clauses | 14 |
| Alternates | 1 |
| Primary specifications | 07 26 00 Vapor Retarders; 32 13 13 Concrete Paving; 32 13 73 Concrete Paving Joint Sealants |
| Primary divisions | Div 03 Concrete |
| Bidders on file | 4 — Cheek Construction, Monument Co, Sahara Concrete, XL Concrete Masonry |

| Check | Verdict |
| --- | --- |
| Scope items complete and undistorted | ☐ OK ☐ Missing ☐ Distorted |
| Primary specifications correct | ☐ OK ☐ Wrong ☐ Incomplete |
| Alternates complete | ☐ OK ☐ Missing |

## RFP-008 — Site Clearing, Demo, Earthwork, Asphalt Paving, &

Open:  00-source-docs/02-trade-scopes-bidform/Scope of Work - 008 Demo, Earthwork, Paving, Utilities, & Striping.docx

| Scope items captured | 102 (verbatim) |
| --- | --- |
| Coordination clauses | 8 |
| Alternates | 3 |
| Primary specifications | 02 41 13 Selective Site Demolition; 32 12 16 Asphalt Paving |
| Primary divisions | Div 31 Earthwork; Div 33 Utilities |
| Bidders on file | 3 — Monument Co, NDX, NewCom TAB |

| Check | Verdict |
| --- | --- |
| Scope items complete and undistorted | ☐ OK ☐ Missing ☐ Distorted |
| Primary specifications correct | ☐ OK ☐ Wrong ☐ Incomplete |
| Alternates complete | ☐ OK ☐ Missing |

## ITB-077 — Lockers

Open:  00-source-docs/02-trade-scopes-bidform/Scope of Work - 077 Lockers.docx

| Scope items captured | 15 (verbatim) |
| --- | --- |
| Coordination clauses | 3 |
| Alternates | 0 |
| Primary specifications | 10 51 13 Metal Lockers |
| Primary divisions | — |
| Bidders on file | 1 — IISI |

| Check | Verdict |
| --- | --- |
| Scope items complete and undistorted | ☐ OK ☐ Missing ☐ Distorted |
| Primary specifications correct | ☐ OK ☐ Wrong ☐ Incomplete |
| Alternates complete | ☐ OK ☐ Missing |

## RFP-016 — Landscaping & Irrigation

Open:  00-source-docs/02-trade-scopes-bidform/Scope of Work - 016 Landscaping & Irrigation.docx

| Scope items captured | 26 (verbatim) |
| --- | --- |
| Coordination clauses | 2 |
| Alternates | 2 |
| Primary specifications | 32 84 00 Landscape Irrigation; 32 91 13 Track & Field Event Inorganic Material Mix; 32 96 50 Invasive Plant Removal |
| Primary divisions | Div 32 Exterior Improvements (as pertains to this scope of work) |
| Bidders on file | 3 — Black Canyon, BrightView, Tand |
| Your rulings applied | RFP-016 carries primary spec sections 32 84 00, 32 91 13 and 32 96 50. |

| Check | Verdict |
| --- | --- |
| Scope items complete and undistorted | ☐ OK ☐ Missing ☐ Distorted |
| Primary specifications correct | ☐ OK ☐ Wrong ☐ Incomplete |
| Alternates complete | ☐ OK ☐ Missing |

# Part D — What is still missing

The coverage audit walked all 378 files under 00-source-docs. 278 are processed, 58 are derived artifacts produced by this pipeline, and 42 have never been opened — 17 of those are high impact and are listed in full below.

Defines the bid line items and alternate structure every exhibit must mirror. package-index-v2.json currently has NO bid_form_line_items field -- the v1 index had one.

- 02.0 - Subcontractor Proposal (Bid) Form (1%).pdf

- Subcontractor Proposal (Bid) Form (1%).pdf

Scope narratives reference the Geotechnical Report 25 times (backfill, hard dig, caliche, compaction). Drives RFP-008 earthwork and RFP-030 foundations. Never opened.

- 04.02 - Geotech Report 012125.pdf

Defines the actual abatement scope for RFP-002. Never opened.

- 04.03 - Asbestos Survey_EICS 100323.pdf

- 04.04 - Asbestos Mgmt Plan & Inspection Reports_EISC 010422.pdf

Scope docs bind subs to these by reference ('multiple mobilizations per the Preliminary Construction Schedule and Logistics Plan'). Never opened.

- 05.7 - Preliminary Construction Schedule (04.21.26).pdf

- Logistics Plan Template.pdf

The Attachment A and B templates -- the output format for Stage 7. Never opened.

- 001_Attach A_PA DS Template_04-03-25.docx

- 002_ Attach A_ Subcontract DS Template_05-09-25.docx

- NV_Attach A Review Log Cover Bluebeam Template_11-14-25.xls

- PrePreparatory Phase Checklist.docx

- NV Attach B_Consultant DS Template  07-11-16.pdf

- NV Attach B_Subcontract Gen Prov DS TEMPLATE_01.28.23.pdf

Product basis-of-design cut sheets tied to specific packages: ACO Sport trench drain (RFP-030), discus cage / pole vault / goal post (ITB-019, RFP-030 footings).

- ACO Sport - System 3000 Slot Channel Trench Drain System Spec Sheet.pdf

- DCHS-35BN Discuss Cage.pdf

- Pole Vault.pdf

- SEF305P Goal Post.pdf

Recommendation

Close the Bid Form and the four cut sheets before reviewing content. The Bid Form is a regression — the v1 index carried bid_form_line_items and v2 lost it — and the cut sheets resolve basis-of-design that has no other source. Defer the Attachment A/B templates, which are Stage 7 output format rather than index input, and read the geotech and asbestos reports while drafting the specific packages they govern (RFP-002, RFP-008, RFP-030) rather than as a blanket pass now.