## GC's
NCSD - Tonopah Field Replacement | [6 empty] | Months Remaining: |  |  | 14.8274 |  |  | Status Date | 2026-07-20
[7 empty] | Weeks Remaining: |  |  | 64.4286 |  |  | Projected Through | 2027-10-14
Code | CORE Team Member | Contract Rate | Title | Original Estimate | Charging Start Date (only enter if start date is later than status date) | Charging End Date (only enter if end date is earlier than projected date) | Hrs Billed per Week | Weeks Remaining | Actual Costs to Date | Remaining Cost | Projection | Monthly Budget 1 Month | Variance | Notes
01-2002-10000 |  | 189 | Project Director |  |  |  | 4 | 64.4286 |  | 48708 | 48708 | 3285 | -48708
01-2003-10000 |  | 174 | Senior Project Manager |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2004-10000 |  | 137 | Project Manager |  | 2026-10-26 |  | 20 | 50.4286 |  | 138174.2857 | 138174.2857 | 9318.8496 | -138174.2857
01-2005-10000 |  | 116 | Assistant Project Manager |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2006-10000 |  | 105 | Project Engineer |  |  |  | 40 | 64.4286 |  | 270600 | 270600 | 18250 | -270600
01-2007-10000 |  | 88 | Project Coordinator |  |  |  | 8 | 64.4286 |  | 45357.7143 | 45357.7143 | 3059.0476 | -45357.7143
01-2010-10000 |  | 200 | Dir. Of Field Operations |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2012-10000 |  | 137 | Project Superintendent |  | 2026-10-26 |  | 40 | 50.4286 |  | 276348.5714 | 276348.5714 | 18637.6993 | -276348.5714
01-2013-10000 |  | 116 | Assistant Superintendent |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2015-10000 |  | 95 | Project Accountant |  |  |  | 4 | 64.4286 |  | 24482.8571 | 24482.8571 | 1651.1905 | -24482.8571
01-2018-10000 |  | 95 | Contract Administrator |  |  |  | 4 | 64.4286 |  | 24482.8571 | 24482.8571 | 1651.1905 | -24482.8571 | PC and CPR
01-2019-10000 |  | 95 | Certified Payroll |  | 2026-10-26 |  | 8 | 50.4286 |  | 38325.7143 | 38325.7143 | 2584.7904 | -38325.7143
01-2020-10001 |  | 75 | Assistant Contract Administrator |  |  |  | 4 | 64.4286 |  | 19328.5714 | 19328.5714 | 1303.5714 | -19328.5714
01-2021-10000 |  | 189 | General Superintendent |  | 2026-10-26 |  | 4 | 50.4286 |  | 38124 | 38124 | 2571.1863 | -38124
01-2030-10000 |  | 12.5 | Vehicle Expenses |  |  |  | 4105 |  |  | 51312.5 | 51312.5 |  | -51312.5
01-2050-10000 |  | 131 | MPE/BIM Manager |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2050-20000 |  | 115 | BIM Manager |  |  |  | 0 | 64.4286 |  | 0 | 0 | 0 | 0
01-2160-10000 |  | 50 | Blueprinting |  |  |  |  | 50.4286 |  | 2521.4286 | 2521.4286 |  | -2521.4286
01-2170-10000 |  | 500 | Photographs |  |  |  |  | 11.6383 |  | 5819.1289 | 5819.1289 |  | -5819.1289 | Drone + progress + final
01-2220-10000 |  | 1375 | Room & Board |  |  |  |  | 50.4286 |  | 69339.2857 | 69339.2857 |  | -69339.2857 | Tommy Subsistence
01-2250-10000 |  | 500 | Travel Expenses |  |  |  |  | 50.4286 |  | 25214.2857 | 25214.2857 |  | -25214.2857
01-2850-10000 |  | 0.0002 | Textura Fee | [6 empty] | 2400 | 2400 |  | -2400
01-5020-10000 |  | 600 | Trailer Rent |  |  |  |  | 11.6383 |  | 6982.9547 | 6982.9547 |  | -6982.9547
01-5021-10000 |  | 100 | Trailer Equipment/Supplies |  |  |  |  | 50.4286 |  | 5042.8571 | 5042.8571 |  | -5042.8571
01-5022-10000 |  | 1000 | Trailer Mobilize/Demobilize |  |  |  |  | 2 |  | 2000 | 2000 |  | -2000
01-5023-10000 |  | 550 | Jobsite Phone/Data |  |  |  |  | 11.6383 |  | 6401.0418 | 6401.0418 |  | -6401.0418
01-5024-10000 |  | 100 | Jobsite Copy Machine |  |  |  |  | 50.4286 |  | 5042.8571 | 5042.8571 |  | -5042.8571
01-5025-10000 |  | 100 | Project Supplies |  |  |  |  | 50.4286 |  | 5042.8571 | 5042.8571 |  | -5042.8571
01-5120-10001 |  | 1000 | Project Identification |  |  |  |  | 1 |  | 1000 | 1000 |  | -1000
01-5160-10000 |  | 1 | Mobile/Cell Service |  |  |  | 5281.5714 |  |  | 5281.5714 | 5281.5714 |  | -5281.5714
01-5240-10000 |  | 40 | Trailer Drinking Water |  |  |  |  | 50.4286 |  | 2017.1429 | 2017.1429 |  | -2017.1429
01-6000-10000 |  | 0.0002 | LCP Tracker | [6 empty] | 2400 | 2400 |  | -2400
01-6002-10000 |  | 0.0011 | Procore | [6 empty] | 13200 | 13200 |  | -13200
01-6003-10000 |  | 0.0002 | Drone Deploy | [6 empty] | 2400 | 2400 |  | -2400
01-6070-10000 |  | 100 | Safety Equipment |  |  |  |  | 50.4286 |  | 5042.8571 | 5042.8571 |  | -5042.8571
01-6075-10000 |  | 300 | Safety - Contract Service |  |  |  |  | 11.6383 |  | 3491.4774 | 3491.4774 |  | -3491.4774
|  |  |  | 0 |  |  |  |  | 0 | 1145884.8172 | 1145884.8172 |  | -1145884.8172
[8 empty] | GMP Value | 12000000
Note on F3: Avery Hacker: Date needs to be entered for any personnel not yet charging to the project
Note on G3: Avery Hacker: Date needs to be entered for any personnel that won't be charging to the end of the project

## Monthly GC's
Job Name - GC's
Monthly GC Calculator
Code | CORE Team Member | Contract Rate | Title | % Allocation | Hrs Billed per Week | Weeks Remaining | Actual Costs to Date | Cost | Projection | Monthly Budget 1 Month | Variance | Notes
01-2003-10000 |  | 138 | Senior Project Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2004-10000 |  | 115 | Project Manager | 50% | 20 | 4.33 | 0 | 9959 | 9959 | #DIV/0! | #REF!
01-2005-10000 |  | 100 | Assistant Project Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2006-10000 |  | 90 | Project Engineer | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2007-10000 |  | 85 | Project Coordinator | 50% | 20 | 4.33 | 0 | 7361 | 7361 | #DIV/0! | #REF!
01-2009-10000 |  | 40 | Intern | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2010-10000 |  | 175 | Dir. Of Field Operations | 10% | 4 | 4.33 | 0 | 3031 | 3031 | #DIV/0! | #REF!
01-2011-10000 |  | 130 | Senior Project Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2012-10000 |  | 120 | Project Superintendent | 100% | 40 | 4.33 | 0 | 20784 | 20784 | #DIV/0! | #REF!
01-2013-10000 |  | 100 | Assistant Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2014-10000 |  | 100 | Assistant Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2015-10000 |  | 90 | Project Engineer | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2017-10000 |  | 85 | Project Accountant | 10% | 4 | 4.33 | 0 | 1472.2 | 1472.2 | #DIV/0! | #REF!
01-2018-10000 |  | 85 | Contract Administrator | 15% | 6 | 4.33 | 0 | 2208.3 | 2208.3 | #DIV/0! | #REF!
01-2021-10000 |  | 150 | General Superintendent | 10% | 4 | 4.33 | 0 | 2598 | 2598 | #DIV/0! | #REF!
01-2022-10000 |  | 120 | MPE Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2023-10000 |  | 85 | Quality Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2030-10000 |  | 10 | Vehicle Expenses |  | 98 | 4.33 | 0 | 4243.4 | 4243.4 |  | #REF!
01-5160-10000 |  | 1 | Mobile/Cell Service |  | 98 | 4.33 | 0 | 424.34 | 424.34 |  | #REF!
01-1100-10000 |  |  | Meeting Supplies | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-2160-10000 |  |  | Blueprinting | per month | 0 | 1 | 0 | 0 | 0 |  | #REF!
01-2170-10000 |  |  | Photographs | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-2175-10000 |  |  | Real Time Video Camera |  | 500 | 0 | 0 | 0 | 0 |  | #REF!
01-2800-10000 |  |  | LCP Tracker |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-2850-10000 |  |  | Textura Fee |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-5015-10000 |  |  | Trailer Mobilize/Demobilize | each | 5000 | 1 | 0 | 5000 | 5000 |  | #REF!
01-5020-10000 |  |  | Trailer Rent | per month | 1000 | 1 | 0 | 1000 | 1000 |  | #REF!
01-5021-10000 |  |  | Trailer Equipment/Supplies | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-5022-10000 |  |  | Jobsite Copy Machine | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-5023-10000 |  |  | Jobsite Phone/Data | per month | 300 | 1 | 0 | 300 | 300 |  | #REF!
01-5030-10000 |  |  | State Trailer |  | 1000 | 0 | 0 | 0 | 0 |  | #REF!
01-5240-10000 |  |  | Trailer Drinking Water | per week | 40 | 4.33 | 0 | 173.2 | 173.2 |  | #REF!
01-6000-10000 |  |  | Submittal Exchange |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6001-10000 |  |  | Multivista |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6002-10000 |  |  | Procore | Per contract | 0.00725% | 10000000 | 0 | 725 | 725 |  | #REF!
01-6065-10000 |  |  | Promotional |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6070-10000 |  |  | Safety Equipment | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-6075-10000 |  |  | Safety - Contract Service | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-7010-10000 |  |  | Detail & Close-Out |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
[7 empty] | 0 | 62078.44 | 62078.44 |  | #REF!