## GC's
SPWD UNLV Business School | UNLV Business School GC's | [6 empty] | Start Date |  |  | 31.8247 |  |  | Status Date | 2028-05-08
[8 empty] | End Date |  |  | 138.2857 |  |  | Projected Through | 2031-01-01
[14 empty] | GMP Amount | 200000000
Code | CORE Team Member | Contract Rate | Title | Original Estimate | Total Hours | Charging Start Date (only enter if start date is later than status date) | Charging End Date (only enter if end date is earlier than projected date) | Hrs Billed per Week | Weeks Remaining | Actual Costs to Date | Remaining Cost | Projection | Monthly Budget 1 Month | Variance | Notes
01-1100-10000 |  |  | Meeting Supplies | [8 empty] | 0 |  | 0
01-2000-10000 |  |  | Quality Control Manager | [5 empty] | 138.2857
01-2001-10000 |  |  | Safety Director | [5 empty] | 138.2857
01-2002-10000 |  | 233 | Project Principal | [5 empty] | 138.2857
01-2003-10000 |  | 178 | Senior Project Manager |  | 5531.4286 |  |  | 40 | 138.2857 |  | 984594.2857 | 984594.2857 | 30938.0952 | -984594.2857
01-2004-10000 |  | 143 | Project Manager |  | 5531.4286 |  |  | 40 | 138.2857 |  | 790994.2857 | 790994.2857 | 24854.7619 | -790994.2857
01-2005-10000 |  | 123 | Assistant Project Manager |  | 5531.4286 |  |  | 40 | 138.2857 |  | 680365.7143 | 680365.7143 | 21378.5714 | -680365.7143
01-2004-20000 |  | 108 | Project Engineer |  | 5531.4286 |  |  | 40 | 138.2857 |  | 597394.2857 | 597394.2857 | 18771.4286 | -597394.2857
01-2006-10000 |  | 108 | Field Engineer |  | 5531.4286 |  |  | 40 | 138.2857 |  | 597394.2857 | 597394.2857 | 18771.4286 | -597394.2857
01-2007-10000 |  | 50 | Intern |  | 5531.4286 |  |  | 40 | 138.2857 |  | 276571.4286 | 276571.4286 | 8690.4762 | -276571.4286
01-2008-10000 |  | 178 | Senior Project Superintendent |  | 5531.4286 |  |  | 40 | 138.2857 |  | 984594.2857 | 984594.2857 | 30938.0952 | -984594.2857
01-2009-10000 |  | 143 | Project Superintendent (Structural and Int Finish) |  | 5531.4286 |  |  | 40 | 138.2857 |  | 790994.2857 | 790994.2857 | 24854.7619 | -790994.2857
01-2010-10000 |  | 123 | Assistant Superintendent (Utilities & Site) |  | 5531.4286 |  |  | 40 | 138.2857 |  | 680365.7143 | 680365.7143 | 21378.5714 | -680365.7143
01-2010-10000 |  | 143 | Project Superintendent (Enclosure) |  | 3137.1429 | 2029-07-01 |  | 40 | 78.4286 |  | 448611.4286 | 448611.4286 | 14096.3474 | -448611.4286
01-2012-20000 |  | 143 | Project Superintendent (MEP) |  | 4520 | 2028-11-01 |  | 40 | 113 |  | 646360 | 646360 | 20310.0379 | -646360
|  | 123 | Assistant Superintendent (Interior Finishes) |  |  | 2029-07-20 |  | 40 | 75.7143 |  | 372514.2857 | 372514.2857 | 11705.2096 | -372514.2857
01-2013-10000 |  | 103 | Project Coordination |  | 800 |  |  | 8 | 138.2857 |  | 113947.4286 | 113947.4286 | 3580.4762 | -113947.4286
01-2014-10000 |  | 103 | Certified Payroll Manager |  | 800 |  |  | 8 | 138.2857 |  | 113947.4286 | 113947.4286 | 3580.4762 | -113947.4286
01-2015-10000 |  | 103 | Project Accountant |  | 553.1429 |  |  | 4 | 138.2857 |  | 56973.7143 | 56973.7143 | 1790.2381 | -56973.7143
01-2016-10000 |  | 103 | Contract Administrator |  | 553.1429 |  |  | 4 | 138.2857 |  | 56973.7143 | 56973.7143 | 1790.2381 | -56973.7143
01-2017-10000 |  | 70 | Assistant Contract Administrator |  | 553.1429 |  |  | 4 | 138.2857 |  | 38720 | 38720 | 1216.6667 | -38720
01-2018-10000 |  | 143 | MEP/Cx Manager |  | 553.1429 |  |  | 4 | 138.2857 |  | 79099.4286 | 79099.4286 | 2485.4762 | -79099.4286
01-2019-10000 |  | 128 | BIM Manager |  | 236.5714 |  | 2028-12-01 | 8 | 29.5714 |  | 30281.1429 | 30281.1429 | 951.4994 | -30281.1429
01-2020-10000 |  | 193 | General Superintendent |  | 1106.2857 |  |  | 8 | 138.2857 |  | 213513.1429 | 213513.1429 | 6709.0476 | -213513.1429
01-2021-10000 |  | 193 | Project Director |  | 1106.2857 |  |  | 8 | 138.2857 |  | 213513.1429 | 213513.1429 | 6709.0476 | -213513.1429
01-2022-10000 |  | 203 | Director of Operations |  |  |  |  | 0 | 138.2857 |  | 0 | 0 | 0 | 0
01-2023-10000 |  |  | Additional Project Team
01-2024-10000 |  |  | Additional Project Team
01-2025-10000 |  |  | Additional Project Team
01-2030-10000 |  | 0 | Vehicle Expenses |  |  |  |  | 51773.7143 |  |  | 0 | 0 |  | 0
01-5160-10000 |  | 1 | Mobile/Cell Service |  |  |  |  | 61811.4286 |  |  | 61811.4286 | 61811.4286 |  | -61811.4286
|  | 500 | Photographs | [5 empty] | 32.2667 | 0 | 16133.3333 | 16133.3333 | 506.9444 | -16133.3333
|  | 500 | Touch Plan | [5 empty] | 32.2667 | 0 | 16133.3333 | 16133.3333 | 506.9444 | -16133.3333
|  | 0.0002 | LCP Tracker |  |  |  |  | 200000000 |  | 0 | 40000 | 40000 | 1256.8871 | -40000
|  | 0.00028 | Procore BIM |  |  |  |  | 200000000 |  | 0 | 56000 | 56000 | 1759.6419 | -56000
|  | 0.0011 | Procore |  |  |  |  | 200000000 |  | 0 | 220000 | 220000 | 6912.8788 | -220000
|  | LS | Trailer Mobilize/Demobilize | [6 empty] | 0 | 25000 | 25000 | 785.5544 | -25000
|  | 6500 | Trailer Rent | [5 empty] | 32.2667 | 0 | 209733.3333 | 209733.3333 | 6590.2778 | -209733.3333
01-5030-10000 |  | 1500 | State Trailer | [5 empty] | 32.2667 | 0 | 48400 | 48400 | 1520.8333 | -48400
|  | 500 | Trailer Equipment/Supplies | [5 empty] | 138.2857 | 0 | 69142.8571 | 69142.8571 | 2172.619 | -69142.8571
|  | 1000 | Jobsite Copy Machine | [5 empty] | 32.2667 | 0 | 32266.6667 | 32266.6667 | 1013.8889 | -32266.6667
|  | 500 | Drinking Water | [5 empty] | 138.2857 | 0 | 69142.8571 | 69142.8571 | 2172.619 | -69142.8571
|  | 0 | Travel | [5 empty] | 32.2667 | 0 | 0 | 0 | 0 | 0
|  | 500 | Meeting Supplies | [5 empty] | 138.2857 | 0 | 69142.8571 | 69142.8571 | 2172.619 | -69142.8571
|  | 100 | Blueprints | [5 empty] | 138.2857 | 0 | 13828.5714 | 13828.5714 | 434.5238 | -13828.5714
|  | 500 | Safety Contract Service | [5 empty] | 32.2667 | 0 | 16133.3333 | 16133.3333 | 506.9444 | -16133.3333
|  | 2000 | Jobsite Data | [5 empty] | 32.2667 | 0 | 64533.3333 | 64533.3333 | 2027.7778 | -64533.3333
| Misc | 5000 | Temp Utilities | [6 empty] | 0 | 27728 | 27728 | 871.2741 | -27728
|  |  |  | 0 | [5 empty] | 0 | 9822853.3333 | 8829534.8571 | 306713.1797 | -8829534.8571
[11 empty] | 4.911% |  | of GMP
GR's
|  |  |  | 0 | [5 empty] | 0 |  | 993318.4762 |  | -993318.4762
Note on G4: Avery Hacker: Date needs to be entered for any personnel not yet charging to the project
Note on H4: Avery Hacker: Date needs to be entered for any personnel that won't be charging to the end of the project

## GR's
GENERAL REQUIREMENTS BREAKDOWN
200000000
Bldng SF | 154034
Total Duration
| 138.2857 | WEEKS | 31.8247 | MOS
DESCRIPTION | QTY. | UNITS | COST | Total Cost
GEN #1 - Gen Temp Construction Requirements |  |  |  | 2266142
Temp Stair Tower (Quantity of 2)
Set up, Removal, and Rental | 18 | MO | 3425 | 61650
Maintenance | 18 | MO | 750 | 13500
Elevated Deck Safety Railings
Safety Railing Materials | 5000 | LF | 10 | 50000
Maintenance (3Hrs/Day for 10 Months) | 779.4 | HR | 90 | 70146
Removal (3 Hrs/Day for 6 Months) | 467.64 | HR | 90 | 42088
Misc Materials | 43.3 | WK | 500 | 21650
Off-Site City Street Requirements
Lane Encroachment Permit | 1 | LS | 10000 | 10000
K-Rail & Fence Barrier
Shipping & Delivery | 1200 | LF | 9.9556 | 11952
Installation of Barriers | 422 | HRS | 102 | 43044
Monthly Barrier Rental | 31.8247 | MO | 4800 | 152759
Fencing, Mounted to K-Rail | 0 | LF | 32.2728 | 0
Monthly Fence Rental | 0 | MO | 2194.1224 | 0
Maintenance of Barricade System (Twice per month) | 1018.389 | HRS | 90 | 91656
Traffic Control | 965 | DAY | 600 | 579000
Street Sweeping, Biweekly | 275.7925 | EA | 350 | 96528
Power Consumption, Construction | 22.8247 | MO | 3000 | 68474
Power Consumption, Start-Up & Commissioning | 9 | MO | 26540.6897 | 238867
Protection of Existing Site Finishes (Maryland Parkway, Water Meters, NVE Vaults & Meter Pedestals, Traffic Signals) | 1 | LS | 75000 | 75000
Water Utility Charges | 9 | MO | 10000 | 90000
Temporary Sanitary Facilities / Job Toilets | 138.2857 | WK | 2250 | 311143
Parking Space Charges | 31.8247 | MO | 7500 | 238685
GEN #2 - Equipment Rental & Operations |  |  |  | 5098628
Forklift #1 (Primary)
Mobilization / Demobilization | 1 | EA | 1500 | 1500
Monthly Rental | 24.8247 | MO | 4500 | 111711
Light Equipment Operator(s) (40 HR / Week) | 4302.6096 | HR | 102 | 438867
Light Equipment Fuel | 5378.2621 | GAL | 9 | 48405
Forklift (Secondary)
Mobilization / Demobilization | 1 | EA | 1500 | 1500
Monthly Rental | 24.8247 | MO | 4500 | 111711
Light Equipment Operator(s) (20 HR / Week) | 2151.3048 | HR | 102 | 219434
Light Equipment Fuel | 2689.131 | GAL | 9 | 24203
Loading Decks (Qty of 3)
Delivery & Pickup | 3 | EA | 1600 | 4800
Installation and Removal (2 Laborers, 3hrs to install, 3hrs to remove) | 18 | HR | 90 | 1620
Rental | 23.5566 | MO | 2500 | 58892
Man & Material Lift
Install/Dismantle/Engineering/Permits | 1 | EA | 60500 | 60500
Monthly Rental | 13 | MO | 8825 | 114725
Operator, Standard Time | 2253.16 | HR | 147 | 331215
Operator, Overtime | 563.329 | HR | 197 | 110976
Loading Dock & Ramp | 1 | EA | 67482 | 67482
Tower Crane
Mobilization / Demobilization | 2 | EA | 53760 | 107520
Monthly Rental | 15 | MO | 150788.4 | 2261826
Operator Crew (2 Man), Standard Time | 2599.8 | HR | 288 | 748743
Operator Crew (2-Man), Overtime | 649.995 | HR | 420 | 272998
GEN #3 - Waste Management & Cleaning |  |  |  | 289018
Waste Management, Building 1 & 2
Standard Waste Dumpster (5/week) | 691.4286 | EA | 380 | 262743
Waste Management Labor | 0 | HR | 95
Waste Management, Offsite
Standard Waste Dumpster (Biweekly) | 69.1429 | WK | 380 | 26275
Waste Management Labor | 0 | HR | 95
6 - Offsite Temp Construction Requirements |  |  |  | 994987
Primary Off-Site Laydown Area
Lease Amount | 31.8247 | MO | 7450 | 237094
Temporary Fence | 1700 | LF | 12.5 | 21250
Lockable Gate Panels | 2 | EA | 600 | 1200
Main Construction Sign | 1 | EA | 1750 | 1750
Site Safety & Security Signage | 17 | EA | 150 | 2550
Gravel (2") to close SWPP | 149500 | SF | 1.55 | 231725
Labor to Set Up Offsite Logistics Plan | 288 | HRS | 85 | 24480
Construction Storage Units (Qty of 3) |  |  |  | 0
Mobilization | 3 | EA | 155 | 465
Monthly Rental | 31.8247 | MO | 525 | 16708
Construction Toilets |  |  |  | 0
Mobilization | 12 | EA | 180 | 2160
Monthly Rental | 31.8247 | MO | 3000 | 95474
Additional Service / Cleaning | 31.8247 | MO | 840 | 26733
Sanitation Station |  |  |  | 0
Mobilization | 6 | EA | 155 | 930
Monthly Rental | 31.8247 | MO | 250 | 7957
Dust Control Service |  |  |  | 0
Monthly Service | 21 | MO | 653.3333 | 13720
Trailer Holding Tank |  |  |  | 0
Mobilization | 1 | EA | 500 | 500
Monthly Rental | 31.8247 | MO | 750 | 23869
Trailer Security System | 23.8685 | MO | 12000 | 286422
11 - Dust Control |  |  |  | 573748
Plan and Permit | 9 | AC | 600 | 5400
Permit Extension (1+ Years) | 2 | EA | 750 | 1500
Metered Connection | 1 | EA | 500 | 500
Construction Water (On-Site) | 31.8247 | MO | 2500 | 79562
Track Out Pad & Maintenance | 31.8247 | MO | 1000 | 31825
Water Truck, Fuel & Maintenance | 138.2857 | WK | 1250 | 172858
Water Truck Operator (20 HR / WK) | 2765.7143 | HR | 102 | 282103
12 - Storm Water Mitigation |  |  |  | 214158
Plan & Permit | 9 | AC | 1800 | 16200
Permit Extension (1+ Years) | 2 | EA | 2500 | 5000
Concrete Washout | 2 | EA | 12500 | 25000
Waddles | 5000 | LF | 6 | 30000
Off-Site
BMP Prevention Methods, Setup | 4 | AC | 1500 | 6000
BMP Prevention Methods, Maintenance (1HR/DAY) | 691.4286 | HRS | 90 | 62229
On-Site
BMP Prevention Methods, Setup | 5 | AC | 1500 | 7500
BMP Prevention Methods, Maintenance (1HR/DAY) | 691.4286 | HRS | 90 | 62229
17 - Tree Protection & Maintenance |  |  |  | 40666
Tree Protection & Maintenance | 31.9145 | MO
Protect Trees - Plastic Jersey Barriers | 56 | EA | 500 | 28000
Quarterly Maintenance | 2 | EA | 2000 | 4000
Pruning
Fertilizer
Water Trees | 21.665 | WK | 400 | 8666
27 - Structural Layout/Coordination |  |  |  | 102636
Placing Embeds for Hangers for Temporary Construction | 480 | HR | 85 | 40800
Materials | 23 | Pour | 2000 | 46000
Equipment and Small Tools | 1 | LS | 15836 | 15836
Total of Items Above |  |  |  | 9579983
37 - Temporary Dry-in |  |  |  | 95200
Temp-In Windows (50%) | 0 | SF | 3.5 | 0
Temporary Enclosure Protection Materials | 34 | WK | 1000 | 34000
Temp Enclosure Labor | 680 | HR | 90 | 61200
55 - Temp Requirements for Phasing/Quality Control |  |  |  | 504102
Finish Protection & Gen Labor
Finish Protection, Materials | 51.996 | WK | 2500 | 129990
General Laborer, Full Time | 4156.8 | HRS | 90 | 374112
58 - Interior Layout & Coordination |  |  |  | 150819
Vertical Gridline Transfer | 154034 | GSF | 0.15 | 23106
Interior Wall Layout | 154034 | GSF | 0.25 | 38509
Carpenter | 820 | HR | 90 | 73800
Consumables | 154034 | GSF | 0.1 | 15404
70 - Progressive and Final Cleaning Req |  |  |  | 682671
Cleaning Materials | 154034 | GSF | 0.1 | 15404
Building (Labor) | 5531.4286 | HR | 90 | 497829
Final Clean Service | 154034 | GSF | 1.1 | 169438
11012775
| Labor/Operator Hours Included | #REF! | total
|  | #REF! | per month
|  | #REF! | per week
5.506%
|  |  | Labor | 2218759
|  |  | GR's minus Man Lift & Crane | 6871478
|  |  | % of $200m | 3.436%
Note on E119: Avery Hacker: Do we still need this?

## Monthly GC's
Job Name - GC's
Monthly GC Calculator
Code | CORE Team Member | Contract Rate | Title | % Allocation | Hrs Billed per Week | Weeks Remaining | Actual Costs to Date | Cost | Projection | Monthly Budget 1 Month | Variance | Notes
01-2003-10000 |  | 138 | Senior Project Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2004-10000 |  | 115 | Project Manager | 50% | 20 | 4.33 | 0 | 9959 | 9959 | #DIV/0! | #REF!
01-2005-10000 |  | 100 | Assistant Project Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2006-10000 |  | 90 | Project Engineer | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2007-10000 |  | 85 | Project Coordinator | 50% | 20 | 4.33 | 0 | 7361 | 7361 | #DIV/0! | #REF!
01-2009-10000 |  | 40 | Intern | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2010-10000 |  | 175 | Dir. Of Field Operations | 10% | 4 | 4.33 | 0 | 3031 | 3031 | #DIV/0! | #REF!
01-2011-10000 |  | 130 | Senior Project Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2012-10000 |  | 120 | Project Superintendent | 100% | 40 | 4.33 | 0 | 20784 | 20784 | #DIV/0! | #REF!
01-2013-10000 |  | 100 | Assistant Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2014-10000 |  | 100 | Assistant Superintendent | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2015-10000 |  | 90 | Project Engineer | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2017-10000 |  | 85 | Project Accountant | 10% | 4 | 4.33 | 0 | 1472.2 | 1472.2 | #DIV/0! | #REF!
01-2018-10000 |  | 85 | Contract Administrator | 15% | 6 | 4.33 | 0 | 2208.3 | 2208.3 | #DIV/0! | #REF!
01-2021-10000 |  | 150 | General Superintendent | 10% | 4 | 4.33 | 0 | 2598 | 2598 | #DIV/0! | #REF!
01-2022-10000 |  | 120 | MPE Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2023-10000 |  | 85 | Quality Manager | 0% | 0 | 4.33 | 0 | 0 | 0 | #DIV/0! | #REF!
01-2030-10000 |  | 10 | Vehicle Expenses |  | 98 | 4.33 | 0 | 4243.4 | 4243.4 |  | #REF!
01-5160-10000 |  | 1 | Mobile/Cell Service |  | 98 | 4.33 | 0 | 424.34 | 424.34 |  | #REF!
01-1100-10000 |  |  | Meeting Supplies | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-2160-10000 |  |  | Blueprinting | per month | 0 | 1 | 0 | 0 | 0 |  | #REF!
01-2170-10000 |  |  | Photographs | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-2175-10000 |  |  | Real Time Video Camera |  | 500 | 0 | 0 | 0 | 0 |  | #REF!
01-2800-10000 |  |  | LCP Tracker |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-2850-10000 |  |  | Textura Fee |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-5015-10000 |  |  | Trailer Mobilize/Demobilize | each | 5000 | 1 | 0 | 5000 | 5000 |  | #REF!
01-5020-10000 |  |  | Trailer Rent | per month | 1000 | 1 | 0 | 1000 | 1000 |  | #REF!
01-5021-10000 |  |  | Trailer Equipment/Supplies | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-5022-10000 |  |  | Jobsite Copy Machine | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-5023-10000 |  |  | Jobsite Phone/Data | per month | 300 | 1 | 0 | 300 | 300 |  | #REF!
01-5030-10000 |  |  | State Trailer |  | 1000 | 0 | 0 | 0 | 0 |  | #REF!
01-5240-10000 |  |  | Trailer Drinking Water | per week | 40 | 4.33 | 0 | 173.2 | 173.2 |  | #REF!
01-6000-10000 |  |  | Submittal Exchange |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6001-10000 |  |  | Multivista |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6002-10000 |  |  | Procore | Per contract | 0.00725% | 10000000 | 0 | 725 | 725 |  | #REF!
01-6065-10000 |  |  | Promotional |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
01-6070-10000 |  |  | Safety Equipment | per week | 100 | 4.33 | 0 | 433 | 433 |  | #REF!
01-6075-10000 |  |  | Safety - Contract Service | per month | 500 | 1 | 0 | 500 | 500 |  | #REF!
01-7010-10000 |  |  | Detail & Close-Out |  | 0 | 0 | 0 | 0 | 0 |  | #REF!
[7 empty] | 0 | 62078.44 | 62078.44 |  | #REF!