## Index
SCOPE COVERAGE ANALYSIS — INDEX
NCSD Tonopah High School Sports Complex ¦ CORE Construction ¦ Per-Scope Coverage in CORE GMP Leveling Format
How to read each tab
Major Scope Items column (A) | Items extracted from SOW, plans, specs, Addendum #1, Clarifications #1 & #2, and the RFI log. These are what a complete proposal MUST cover.
Bidder columns (C onward) | Coverage symbol per bidder: √ = included, O = excluded/missing, ? = needs clarification at descope, + / − = priced add/deduct value, √+ = scope double-counted.
BASE BID row | BC Form submitted value (not normalized). Bond rate row below.
BREAKOUTS section | Sub-pricing or phase breakouts requested from sub.
ALTERNATES section | Required SOW alts + voluntary adds.
KEY NOTES & SCOPE GAPS | Pre-con flags — responsiveness issues, scope basis variances, hidden exclusions.
Symbol Color Code | Green fill = included. Red fill = missing. Amber fill = unclear / has add-deduct value attached.
Package | Scope | # Bidders | Front-Runner | Tab Link
BP 002 | Hazardous Material Abatement & Building Wrecking (Combined 002+004) | 5 | Pair NorthStar (combined) OR Action Solutions (abate) + GGG (wrecking) after resolving plans-acknowledgment and bond rate. | Go to BP002
BP 008 | Site Clearing, Demo, Earthwork, Asphalt Paving & Wet Utilities | 3 | NDX — best scope coverage. Push voluntary adds back to base via descope; strike escalation clauses; confirm Clark Co. wage rates were used. Monument is INVESTIGATE-only until missing alts and license coverage resolved. | Go to BP008
BP 016 | Landscaping & Irrigation | 3 | Black Canyon front-runner pending Alt 016.01 closure and Shot Put assignment. | Go to BP016
BP 021 | Running Track Surfacing | 2 | Confirm Elite base bid value; both bidders are Track surfacing specialists — verify warranty terms. | Go to BP021
BP 022 | Synthetic Turf Sports Field | 6 | Tand (turf only) OR CG&B (combined) front-runners. Resolve RFI 15 deduct-alt restructure across all bidders. | Go to BP022
BP 023 | Fencing & Gates | 6 | All 5's front-runner — clean submission. Tahoe scope verification needed before considering for award. | Go to BP023
BP 030 | Concrete (Cast-in-Place, Site Flatwork, Foundations) | 4 | Monument front-runner on base — push for Alt 030.02 / .03 pricing in descope. | Go to BP030
BP 031 | Masonry (CMU at Concessions Building) | 4 | Henderson Masonry front-runner on base — verify RFI 26 assembly inclusion + segmented retaining wall alt. | Go to BP031
BP 033 | Structural Steel & Ornamental Metals | 2 | Investigate Corona scope completeness vs Adams & Smith. Get Alts 033.02-.04 pricing from both. | Go to BP033
BP 045 | Metal Roofing, Fascia & Soffit Panels | 1 | Sole bidder — validate $49,700 against CORE historical $/SF and verify bond rate. | Go to BP045
BP 061 | Metal Stud Framing, Drywall & Painting (incl. FRP) | 3 | M & H most scope-complete; verify Division 09 Form + backup before considering. | Go to BP061
BP 094 | Bleachers & Press Box (Supply + Install) | 1 | Sole bidder — validate $/seat, confirm install scope, get scoreboard + ticket booth alts priced. | Go to BP094
BP 098 | Plumbing Systems | 4 | Bombard front-runner; reconcile Alt 098.01-A scope basis across all bidders. | Go to BP098
BP 100 | HVAC & Building Controls Systems (incl. T&B) | 3 | Evaluate U.S. Mechanical combined BP 098+100 award; push Alt 100.03 deduct in descope. | Go to BP100
BP 103 | Electrical & Low Voltage Systems (incl. Sports Field Lighting) | 5 | Quantum Electric — best balance of price + responsiveness. Investigate JW Electric scope before relying on its $807K. | Go to BP103
BP 109 | Prefabricated Ticket Booth (Supply) | 3 | Pending final size selection — Porta-King if cert verified, otherwise Guardian. | Go to BP109

## BP002
BP #002 — Hazardous Material Abatement & Building Wrecking (Combined 002+004)
Asbestos abatement of Bldgs 3-7 (per RFI 16) + full building wrecking at abandoned Tonopah ES (Idaho Cir).
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | GGG Demolition | NorthStar Contracting | Action Solutions (Abate) | Earth Resource Grp (Abate) | Environmental Protection (EPS)
BASE BID (as submitted) | BC Form §Base | 1256279 | 718623 | 304455 | 337395 | 40000
P&P Bond Rate | Form §Bonding | 1.2% | 1.5% | 4% | 2.6% | 2.3%
BASE BID — MAJOR SCOPE ITEMS
ACM Removal — VCT / Floor Mastic (Bldgs 3-7) |  | √ | √ | √ | √ | O
ACM Removal — Asbestos drywall (Bldgs 3-7) |  | √ | √ | √ | √ | O
ACM Removal — Transite piping (Alt 002.01 UR) |  | ? | ? | ? | +$75/LF + $5K mob | O
Lead-based paint (if encountered) |  | ? | ? | ? | ? | O
OSHA Class I / II Containment |  | √ | √ | √ | √ | O
Air monitoring (third-party clearance) |  | ? | ? | ? | ? | O
Bldgs 1-7 wrecking (Bldgs 1-2 to remain per SOW) |  | √ | √ | O | O | O
Concrete pad / footings removal |  | √ | √ | O | O | O
Trees / stump removal at ES |  | √ | √ | O | O | O
Existing fencing demo at ES |  | √ | √ | O | O | O
Site clearing & rough grade at ES |  | √ | √ | O | O | O
Haul-off and legal disposal |  | √ | √ | √ | √ | O
Permits, abatement filings (NRS/AQ) |  | ? | ? | ? | ? | ?
Dust control (Nye Co. AQ) |  | ? | ? | ? | ? | ?
SWPPP / BMP |  | ? | ? | O | O | +$3,225 BMP removal
Stand-alone abatement only |  |  |  | √ scope | √ scope | ?
Cover letter / formal proposal incl. |  | √ | √ | O | √ | √
BREAKOUTS
Combined Pkg 002+004 |  | √ | √ | — | — | —
Abatement (Bldgs 3-7) only |  | — | — | √ | √ | —
Wrecking (Bldgs 1, 7) only |  | — | — | — | — | —
ALTERNATES
Alt 002.01 — Transite Pipe Unit Rate ($/LF) |  | O | O | O | +$75/LF | O
Alt 004.01 — BREAKOUT Work at ES |  | +$0 (combined) | +$23,342 | +$0 | +$0 | +$0
Alt 004.02 — ADD Pkg 002 Abatement to 004 |  | ? | ? | — | — | —
Site Demo at ES (Voluntary or Alt 008.07) |  | +$0 | +$23,342 | — | — | —
KEY NOTES & SCOPE GAPS
• GGG (CA-based) — 60%+ premium to NorthStar.
• NorthStar Bid Docs - HS Sports Plans = NO (responsiveness flag). Bond field $10,773.95 = value not rate; ≈1.5% rate.
• Action and Earth Resource are abatement-only — pair with wrecking sub for full coverage.
• EPS $40K — almost certainly NOT a true abatement bid; SWPPP-only items priced.
• Alliance (LATE) — non-responsive per NRS 338.16995.
CORE PRE-AWARD RECOMMENDATION
Pair NorthStar (combined) OR Action Solutions (abate) + GGG (wrecking) after resolving plans-acknowledgment and bond rate.

## BP008
BP #008 — Site Clearing, Demo, Earthwork, Asphalt Paving & Wet Utilities
Site demo, earthwork, AC paving (track only per RFI 1), wet utilities, & striping. Subbase under turf in base per SOW §7.b.ii (modified by RFI 14/15). Includes ES alt scope.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | NDX, LLC | TAB Contractors (NewCom) | The Monument Company
BASE BID (as submitted) | BC Form §Base | 3152032.69 | 1924851 | 2296000
P&P Bond Rate | Form §Bonding | 2% | 1% | 1%
BASE BID — MAJOR SCOPE ITEMS
Temp construction trailer pad (10K SF fractured rock) |  | √ | √ | ?
Trackout pads + rumble plates (≥2 entrances) |  | √ | √ | ?
Street sweeping (for own work only per TAB) |  | √ | √ (own only) | ?
Stand tank + temp water from hydrant (per SOW §1.d) |  | ? | O (excluded) | ?
SWPPP prep, filing, fees, maintenance (SOW §1.e) |  | √ | O (permits excluded) | ?
Dust control per Nye Co. AQ (SOW §1.f) |  | ? | O (caliche excl) | ?
Dust palliative at completion (SOW §1.g) |  | O (excluded) | O | ?
Salvage equipment turnover (irrigation, flag) §2.a |  | ? | ? | ?
Site demo — curbs, gutters, AC paving, existing track |  | √ | √ | ?
Site demo — existing fencing & footings §2.g |  | √ | √ | ?
Site demo — existing field lights, flag pole §2.h |  | √ | √ | ?
Site demo — bleachers, press box, footings §2.i |  | √ | √ | ?
Site demo — athletic equipment, sand pit materials §2.j |  | O (sports pit material excl) | √ | ?
Sawcutting as required §2.k |  | √ | √ | ?
Demo existing artificial turf §2.l |  | √ | √ | ?
Demo existing landscaping + stump grinding §2.m |  | √ | √ | ?
Existing tree continued irrigation coord (BP 016) §2.m.ii |  | ? | ? | ?
Clear & haul organics / waste / unsatisfactory §2.n |  | √ | √ | ?
Protect items to remain (transformer, vaults) §2.p |  | √ | √ | ?
Domestic water system — tie-in, piping, valves §3 |  | √ | √ | ?
Ductile iron / Cu / PVC piping w/ thrust blocks §3.a.i |  | √ | √ | ?
Flush, test, disinfect, chlorinate §3.c |  | √ | ? | ?
GPS as-builts + drafted plan §3.d |  | ? | ? | ?
Sanitary sewer — tie to existing MH, piping §4 |  | √ | √ | ?
Shoring at deep MHs if required §4.a.i |  | ? | ? | ?
Concrete encasement at water crossings §4.a.ii |  | √ | ? | ?
Camera sewer to 5' outside bldg §4.b |  | ? | ? | ?
GPS as-builts + AutoCAD + drafted plan §4.c |  | ? | ? | ?
Storm drainage — piping, CB, DI, MH, headwalls §5.a |  | √ | √ | ?
Perforated SD piping at sand pits + gravel bed §5.b |  | +$25,072 (carried as alt) | O (3/8" chip stone excl) | ?
Perforated SD along turf straight sides §5.c |  | +$113,870 slot drains (carried as alt) | O | ?
Wet util excavation / trenching / shoring §6.e |  | √ | √ | ?
Wet util bedding / backfill / compaction §6.f |  | √ | √ | ?
Thrust blocks / slurry / encasement §6.g |  | √ | √ | ?
Hard digging / caliche per geotech §6.h |  | ? | O (excluded) | ?
Site grading / over-excavation / scarification §7.a |  | √ | √ | ?
Class D seismic / SDS 1.0 §7.a.ii |  | ? | ? | ?
Building pad — Type II + certified pad §7.a |  | √ (1,012 TON, $78K) | √ | ?
Subbase under turf (6" Type II per RFI 14/15) |  | +$156,600 sand+geo-liner (alt) | O (leveling sand excl) | ?
Type II under all curbs + AC paving §7.c |  | √ | √ | ?
Rip rap as indicated §7.d |  | O (no line item) | ? | ?
Footing backfill at exterior bldg §7.f |  | O (excluded in backup) | ? | ?
Drainage grading per civil §7.f.i |  | √ | √ | ?
Spoils disposal off-site (no stockpiling) §7.g |  | √ | √ | ?
AC paving @ running track (4" per RFI 6) §8 |  | √ (69,100 SF, $620K) | √ (Wells Cargo) | ?
AC subsurface tolerance per track sub §8.b |  | √ | √ | ?
In-house AC mix testing §8.c |  | ? | ? | ?
Survey request 48 hrs notice / monument protection §9.a |  | √ | √ | ?
Call Before You Dig + locates §9.b |  | ? | O (permits by others) | ?
Wet util testing scheduling + walks §9.d |  | √ | ? | ?
Record drawings (AHJ requirement) §9.h |  | ? | ? | ?
Site striping / signage / bumpers (pkg title) |  | O (excluded) | O (excluded) | ?
Asphalt + fuel material escalation language |  | O (incl in backup — strike) | ? | ?
BREAKOUTS
Phase 1 — Lights, Bleacher demo / prep |  | ? | ? | ?
Phase 2 — Field, Track, Concessions |  | ? | ? | ?
Football field / track / sports field grading |  | √ (~$462K SOV) | ? | ?
Parking lot + shot put areas |  | √ (~$455K SOV) | ? | ?
Concessions building pad |  | √ | ? | ?
Bleachers & press box footing demo |  | √ | ? | ?
Incidental site work |  | √ (~$923K SOV) | ? | ?
Wet utilities (separate backup sheet) |  | √ ($387,512) | ? | ?
ALTERNATES
Alt 008.02 — DEDUCT Combine w/ BP #004 Building Wrecking |  | -$6,000 | O (not priced) | O (not priced)
Alt 008.03 — DEDUCT Combine w/ BP #016 Landscaping |  | O | O | O
Alt 008.04 — Caliche Unit Rate ($/CY) |  | +$46/CY | +$40/CY | +$500/CY
Alt 008.05 — ADD Winterization Plan |  | O | O | O
Alt 008.06 — Type II Site Concrete Unit Rate |  | O | O | O
Alt 008.07 — ADD Demo & Site Clearing at ES (Idaho Cir) |  | +$1,498,400 (full demo + abate) | +$45,000 (rough grade only) | +$0 (likely no-bid)
Alt 008.08 — ADD Propane Gas System at ES |  | O (not priced) | O (excluded) | +$0 (likely no-bid)
Voluntary: S&I 2" Sand + Geo-liner under Turf (RFI 14/15 in base) |  | +$156,600 | O | ?
Voluntary: S&I ACO Slot Drain System 3000 along turf perimeter |  | +$113,870.40 | O | ?
Voluntary: S&I 4" Perf Pipe at LJ/TJ sand pits (SOW §5.b — IN base) |  | +$25,071.80 | O | ?
KEY NOTES & SCOPE GAPS
• Per RFI 1: NO AC paving at parking/driveway — graded earth only. Track AC is the only AC scope.
• Per RFI 6: Track AC = 4" Type II.
• Per RFI 8: No slope stabilization required.
• Per RFI 14/15 (CRITICAL): Subbase + gravel under turf in base; geo liner / leveling sand by BP 022; CORE may pay ADD alts on BP 008 for those items (deduct alts on BP 022).
• Per Clarification #2: Prevailing wage CHANGED to Clark County rates (CL-2026-100) — confirm all 3 bidders priced Clark Co., not Southern NV Rural Region.
• NDX backup has asphalt + fuel-cost escalation language — must strike per GMP firm-price requirement.
• TAB clarifications conflict directly with SOW: water, permits, caliche, traffic control, striping/signs, leveling sand all excluded.
• Monument submission is bare-bones: 4 of 6 required alts not priced; $0 entries on .07/.08 likely 'no bid'; no formal letter; no lower-tier subs listed despite scope demanding A-13/A-19 sub-classifications.
CORE PRE-AWARD RECOMMENDATION
NDX — best scope coverage. Push voluntary adds back to base via descope; strike escalation clauses; confirm Clark Co. wage rates were used. Monument is INVESTIGATE-only until missing alts and license coverage resolved.

## BP016
BP #016 — Landscaping & Irrigation
Landscape planting, irrigation, decorative rock; coordinate with BP 008 / 022 / 023.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Black Canyon | BrightView (GTI 1) | Tand Inc.
BASE BID (as submitted) | BC Form §Base | 111275 | 131300 | 256800
P&P Bond Rate | Form §Bonding | 1.4% | 1.4% | 1.4%
BASE BID — MAJOR SCOPE ITEMS
Landscape planting (trees, shrubs, ground cover) |  | √ | √ | √
Decomposed granite ground cover |  | √ | √ | √
Irrigation mainline / laterals / heads |  | √ | √ | √
Irrigation controller (Hunter / Rain Bird) |  | √ | √ | √
Backflow preventer + connection |  | O | √ | √
Tie-in to existing irrigation source |  | √ | ? | ?
Existing tree continued irrigation (per SOW 008) |  | √ | ? | ?
Hand-watering establishment period |  | ? | ? | ?
90-day landscape maintenance |  | ? | ? | ?
1-year warranty |  | √ | √ | √
Fertilizer / soil amendments |  | √ | ? | ?
Shot put / discus rock material (L1.06 C&D) |  | +$138,300 vol add (excl. survey, conc., cages, fence) | +$103,444 vol add (Discuss & Shot Put rock S&I) | O
Mulch at planting areas |  | √ | √ | √
BREAKOUTS
Irrigation only |  | ? | ? | ?
Planting only |  | ? | ? | ?
Shot Put / Discus (assignment?) |  | ? | ? | —
ALTERNATES
Alt 016.01 — DEDUCT Combine w/ BP #022 Turf |  | O | O | O
Alt — Decorative Rock Ground Cover at East Slope |  | +$26,400 | +$26,400 | +$9,500
KEY NOTES & SCOPE GAPS
• BUILDING CONNECTED DATA QUALITY ISSUE — BrightView's BC slot is tagged to Black Canyon ($111,275). Actual BrightView/GTI 1 Form base = $131,300.
• Tand $256,800 — 2x Black Canyon. Walk through scope coverage at descope.
• Shot Put/Discus assignment is unclear — see RFI 14 / 15 (turf split); confirm whether L1.06 detail belongs to BP 016 or BP 019.
CORE PRE-AWARD RECOMMENDATION
Black Canyon front-runner pending Alt 016.01 closure and Shot Put assignment.

## BP021
BP #021 — Running Track Surfacing
Polyurethane running track surfacing; per RFI 24 = min 2 coats structural over manufacturer base. AC subbase by BP 008.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Elite Sports Builders | The Monument Company
BASE BID (as submitted) | BC Form §Base | (value not parsed) | 756154
P&P Bond Rate | Form §Bonding | 1% | 1%
BASE BID — MAJOR SCOPE ITEMS
Track surfacing — Stobitan SC (or equiv) — 2 coat min |  | √ | √
Manufacturer base mat / shock layer |  | √ | √
Lane line markings (8 lanes) |  | √ | √
Event line markings (long jump, hurdles, etc.) |  | √ | √
AC subgrade acceptance (per BP 008) |  | ? | ?
Discus / hammer cage interface |  | ? | ?
Field event areas (long jump, triple jump pits) |  | ? | ?
IAAF / NFHS certification |  | ? | ?
Manufacturer warranty (5-yr typ) |  | ? | ?
Submittals / shop drawings |  | √ | √
On-site mock-up if required |  | ? | ?
BREAKOUTS
Track surfacing only |  | ? | ?
Field event surfacing |  | ? | ?
Markings / inlays |  | ? | ?
ALTERNATES
Alt 021.01 — ADD Track & Field Equipment (combined) |  | +$0 | +$0
KEY NOTES & SCOPE GAPS
• Elite — base bid value not parsed by BC system. Confirm in writing.
• Monument also bid BP 008, 022, 030 — capacity stack check needed.
• Both bidders entered $0 on Alt 021.01 — confirm intent.
CORE PRE-AWARD RECOMMENDATION
Confirm Elite base bid value; both bidders are Track surfacing specialists — verify warranty terms.

## BP022
BP #022 — Synthetic Turf Sports Field
Synthetic turf field; per RFI 15 = base bid is turf above shock pad. Geo liner, leveling sand, drainage, header board to be priced as DEDUCT alts.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | AstroTurf Corp. | CG&B Enterprises | Green Living Svcs | The Monument Co | Sprinturf, LLC | Tand Inc.
BASE BID (as submitted) | BC Form §Base | 609151 | 1139000 | 1277013 | 1281315 | 1022155 | 799600
P&P Bond Rate | Form §Bonding | 1.5% | 0.75% | 1.6% | 1% | 1.25% | 1.4%
BASE BID — MAJOR SCOPE ITEMS
Synthetic turf carpet (specify pile / fiber) |  | √ | √ | √ | √ | √ | √
Infill material (crumb rubber / coated sand) |  | √ | √ | √ | √ | √ | √
Shock pad (per spec / mfr) |  | √ | √ | √ | √ | √ | √
Field markings — football |  | √ | √ | √ | √ | √ | √
Field markings — soccer (overlay) |  | ? | ? | ? | ? | ? | ?
Field markings — lacrosse (overlay) |  | ? | ? | ? | ? | ? | ?
End-zone inlays / school logos |  | ? | ? | ? | ? | ? | ?
Header board attachment / fastening |  | √ | √ | √ | √ | √ | √
Manufacturer 8-year warranty |  | ? | ? | ? | ? | ? | ?
Submittals / shop drawings |  | √ | √ | √ | √ | √ | √
Acceptance of subgrade (per BP 008) |  | ? | ? | ? | ? | ? | ?
Grooming equipment supply (if specified) |  | ? | ? | ? | ? | ? | ?
BREAKOUTS
Turf + shock pad ONLY (per RFI 15) |  | ? | ? | ? | ? | ? | ?
Geo Liner (deduct alt) |  | ? | ? | ? | ? | ? | ?
Leveling Sand (deduct alt) |  | ? | ? | ? | ? | ? | ?
Field Drainage (deduct alt) |  | ? | ? | ? | ? | ? | ?
Header Board (deduct alt) |  | ? | ? | ? | ? | ? | ?
ALTERNATES
Alt 022.01 — ADD Track & Field Equipment |  | +$395,930 | +$0 | +$0 | +$0 | — | no bid
Alt 022.02 — ADD Storm Drainage System |  | +$1,034,733 | +$126,000 | +$0 | +$0 | — | no bid
Sprinturf — Decorative Rock E. Slope (form-fill error, BP 016 alt) |  | — | — | — | — | +$0 | —
KEY NOTES & SCOPE GAPS
• AstroTurf — 3 portal numbers ($609K turf / $395.9K track / $1.03M drainage). $609K is turf-only. Total if all 3 = $2.04M.
• CG&B bond shows 0.01% in BC; cover note says 0.75%.
• Green Living / Tand — declared no-bid on storm drainage alt.
• Sprinturf entered BP 016 alt by mistake. Resubmit Alt 022.01 / .02 pricing.
• Per RFI 15, geo liner / sand / drainage / header are DEDUCT alts — bidders' BC entries do not match new RFI structure. Request resubmit.
CORE PRE-AWARD RECOMMENDATION
Tand (turf only) OR CG&B (combined) front-runners. Resolve RFI 15 deduct-alt restructure across all bidders.

## BP023
BP #023 — Fencing & Gates
Chain link site fencing + ornamental gates; demo + dispose existing fencing; temp fencing per RFI 17; gate hardware per Section 08 71 00 added by Addendum #1.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | All 5's Construction | Fencing Specialists | Golden Bay Fence | ` | Tahoe Fence | Tiberti Fence
BASE BID (as submitted) | BC Form §Base | 399056 | (not parsed) | 359360 | (not parsed) | 215392 | 277984
P&P Bond Rate | Form §Bonding | 1.1% | 2% | 1.4% | 2% | 3% | 0%
BASE BID — MAJOR SCOPE ITEMS
Chain link perimeter fencing (6'H per RFI 22, A1-20 ctrls) |  | √ | √ | √ | √ | √ | √
Ornamental fencing (where indicated) |  | ? | ? | ? | ? | ? | ?
Walk gates |  | √ | √ | √ | √ | √ | √
Vehicle / double gates |  | √ | √ | √ | √ | √ | √
Gate hardware (Section 08 71 00 + 32 31 13 §2.04) |  | ? | ? | ? | ? | ? | ?
Backstop / ball-stop netting (if specified) |  | ? | ? | ? | ? | ? | ?
Footings (6" below post bottom per RFI 13) |  | √ | √ | √ | √ | √ | √
Demo existing fencing (HS) (by SOW 008 per RFI 10) |  | ? | ? | ? | ? | ? | ?
Haul / dispose existing fencing spoils (per RFI 12) |  | ? | ? | ? | ? | ? | ?
Bleacher under-fencing 6'H (per RFI 11) |  | ? | ? | ? | ? | ? | ?
Temp fencing 2,800 LF HS (per RFI 17) |  | +$125K vol add (HS+ES temp) | ? | ? | ? | ? | ?
Temp fencing 2,300 LF ES (per RFI 17) |  | +$125K vol add (HS+ES temp) | ? | ? | ? | ? | ?
Post sizes per A1-20 (RFI 22 — overrides spec) |  | ? | ? | ? | ? | ? | ?
BREAKOUTS
Permanent fencing HS (base scope) |  | √ | ? | √ | ? | √ | √
Temporary fencing HS + ES |  | +$125K | ? | ? | ? | ? | ?
ES permanent fencing (Alts 023.01-A/B/C) |  | — | — | — | — | — | —
ALTERNATES
Alt 023.01-A — Fencing at ES per AD1.13 |  | +$36,307 | +$5,619.68 | +$28,125 | +$0 | +$7,659 | +$22,381
Alt 023.01-B — Fencing at ES per AD1.16 |  | +$25,640 | +$10,788.76 | +$19,500 | +$0 | +$4,926 | +$17,872
Alt 023.01-C — Propane Tank Enclosure (150 LF, 6'H, 1 pr gates per RFI 9) |  | +$26,980 | +$12,025.61 | +$10,000 | +$0 | +$13,030 | +$17,315
Alt 023.02 — Salvage HS Track fencing (per RFI 10, reuse posts) |  | -$10,815 | +$8,908.58 | +$0 | +$0 | -$20 | +$1,800
KEY NOTES & SCOPE GAPS
• All 5's — most responsive submission; included $125K voluntary for temp fencing per RFI 17.
• Fencing Specialists & Red Star — base bid value not parsed by BC; verify.
• Tahoe — alt values 50-80% below market; scope verify.
• Tiberti — 0% bond likely parse issue.
• Per RFI 22, A1-20 takes precedence on post sizes (overrides spec 32 31 13).
CORE PRE-AWARD RECOMMENDATION
All 5's front-runner — clean submission. Tahoe scope verification needed before considering for award.

## BP030
BP #030 — Concrete (Cast-in-Place, Site Flatwork, Foundations)
Concessions building foundations + slab-on-grade; site flatwork; mow curbs; equipment pads; flagpole footing.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Cheek Construction | The Monument Company | Sahara Concrete | XL Concrete Masonry
BASE BID (as submitted) | BC Form §Base | 1294656 | 1113208 | 1518456 | 1605417
P&P Bond Rate | Form §Bonding | 2.5% | 1% | 1.5% | 1.5%
BASE BID — MAJOR SCOPE ITEMS
Concessions bldg footings / spread footings |  | √ | √ | √ | √
Concessions bldg slab-on-grade w/ vapor barrier |  | √ | √ | √ | √
Stem walls / grade beams |  | √ | √ | √ | √
Reinforcement (rebar / WWF) |  | √ | √ | √ | √
Anchor bolts / embeds (BP 033 coord) |  | √ | √ | √ | √
CMU bond beam coordination (BP 031) |  | ? | ? | ? | ?
Site flatwork — sidewalks |  | √ | √ | √ | √
ADA-compliant ramps / curb cuts |  | √ | √ | √ | √
Mow curbs around turf (per BP 016 interface) |  | √ | √ | √ | √
Concrete steps (bleacher access) |  | ? | ? | ? | ?
Equipment pads (HVAC / transformer) |  | ? | ? | ? | ?
Header board for turf field (per RFI 15 alt) |  | ? | ? | ? | ?
Concrete curing / sealing |  | √ | √ | √ | √
Form work / shoring |  | √ | √ | √ | √
Joint sealants (BP 040 interface) |  | ? | ? | ? | ?
Footing excavation (BP 008 interface) |  | ? | ? | ? | ?
Footing backfill (BP 008 per SOW §7.f) |  | ? | ? | ? | ?
BREAKOUTS
Building concrete (foundations + slab) |  | ? | ? | ? | ?
Site flatwork |  | ? | ? | ? | ?
Curbs |  | ? | ? | ? | ?
ALTERNATES
Alt 030.01 — Flagpole Footing & Install |  | +$14,398.56 | +$11,000 | +$16,500 | +$9,672
Alt 030.02 — Type II Unit Rate ($/CY or $/TON) |  | O | O | O | O
Alt 030.03 — Concrete Finishing (add) |  | O | O | O | O
Header Board (alt per RFI 15) |  | ? | ? | ? | ?
KEY NOTES & SCOPE GAPS
• Monument lowest base; misses Alt 030.02 and Alt 030.03 (all four bidders missed these).
• XL Concrete Masonry also bid BP 031 — combined-award opportunity.
• Cheek 2.5% bond is on high end of market.
• Per RFI 15, header board may be carried as concrete alt — confirm assignment.
CORE PRE-AWARD RECOMMENDATION
Monument front-runner on base — push for Alt 030.02 / .03 pricing in descope.

## BP031
BP #031 — Masonry (CMU at Concessions Building)
CMU walls at concessions building per RFI 26 assembly (rigid + air barrier + furring); mortar/grout/reinforcing; lintels & bond beams.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Henderson Masonry | John Jackson Masonry | Kemper Masonry | XL Concrete Masonry
BASE BID (as submitted) | BC Form §Base | 189449 | 425394 | 355230 | 267417
P&P Bond Rate | Form §Bonding | 1.5% | 1.65% | 2.5% | 1.5%
BASE BID — MAJOR SCOPE ITEMS
CMU walls — exterior (per A4-10 / RFI 26 assembly) |  | √ | √ | √ | √
CMU walls — interior / restroom vestibule (per RFI 26) |  | √ | √ | √ | √
Mortar / grout |  | √ | √ | √ | √
Reinforcing (vert + horiz) |  | √ | √ | √ | √
Bond beams / lintels |  | √ | √ | √ | √
Cleanouts at grouted cells |  | ? | ? | ? | ?
Lift heights per IBC / spec |  | ? | ? | ? | ?
CMU color / finish per spec |  | ? | ? | ? | ?
Rigid insulation 2" attachment (per RFI 26) |  | ? | ? | ? | ?
Fluid-applied air & water barrier (RFI 26) |  | ? | ? | ? | ?
Extended masonry fasteners (per keynote 6-02) |  | ? | ? | ? | ?
Anchor bolts / embeds coord w/ BP 033 |  | ? | ? | ? | ?
CMU footing dowels coord w/ BP 030 |  | ? | ? | ? | ?
Cold-weather protection (if needed) |  | ? | ? | ? | ?
BREAKOUTS
CMU walls only |  | ? | ? | ? | ?
Bond beams / lintels |  | ? | ? | ? | ?
ALTERNATES
Alt 025.01 / 031.01 — Segmented Block Retaining Walls (SOW typo) |  | O | O | O | O
KEY NOTES & SCOPE GAPS
• Henderson lowest base — 2x delta to others. Walk through scope coverage at descope.
• XL Concrete Masonry also bid BP 030 — combined-award opportunity.
• Monument Construction (LATE) — non-responsive per NRS 338.16995.
• SOW alternate is mis-numbered '025.01' — verify intent.
• RFI 26 modified exterior CMU wall assembly — confirm all bidders included rigid + AWB + furring.
CORE PRE-AWARD RECOMMENDATION
Henderson Masonry front-runner on base — verify RFI 26 assembly inclusion + segmented retaining wall alt.

## BP033
BP #033 — Structural Steel & Ornamental Metals
Structural columns, beams, joists, decking at concessions building; misc steel; ornamental; canopy salvage/reinstall at ES.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Adams & Smith | Corona Steel
BASE BID (as submitted) | BC Form §Base | 282164 | 145468
P&P Bond Rate | Form §Bonding | 1% | 2.5%
BASE BID — MAJOR SCOPE ITEMS
Structural columns |  | √ | √
Beams / girders |  | √ | √
Joists |  | √ | √
Roof deck (gauge per spec) |  | √ | √
Lintels / embeds (BP 030/031 coord) |  | √ | √
Misc steel (handrails, etc.) |  | ? | ?
Ornamental metals |  | ? | ?
Anchor bolts (set by BP 030) |  | ? | ?
Deck attachment per spec |  | ? | ?
Shop drawings / engineering |  | √ | √
Galvanizing / shop coatings |  | ? | ?
Field painting (BP 060 interface) |  | ? | ?
Erection / cranes |  | √ | √
BREAKOUTS
Structural steel only |  | ? | ?
Misc / ornamental |  | ? | ?
ALTERNATES
Alt 033.01 — Canopies at ES (salvage / reinstall) |  | +$0 | +$53,519
Alt 033.02 — Scoreboard Posts |  | O | O
Alt 033.03 — Press Box Steel Structure |  | O | O
Alt 033.04 — Steel Plates at Gates |  | O | O
KEY NOTES & SCOPE GAPS
• Corona Steel base 51% of Adams & Smith — scope coverage check required.
• Both bidders missed Alts 033.02, .03, .04.
• Adams & Smith $0 ES Canopies — verify intent (no-bid vs included).
• Corona 2.5% bond is high.
CORE PRE-AWARD RECOMMENDATION
Investigate Corona scope completeness vs Adams & Smith. Get Alts 033.02-.04 pricing from both.

## BP045
BP #045 — Metal Roofing, Fascia & Soffit Panels
Standing-seam metal roofing per spec 07 6100 (PBR panel takes precedence per RFI 23); fascia, soffit, trim.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Canyon State Enterprises
BASE BID (as submitted) | BC Form §Base | 49700
P&P Bond Rate | Form §Bonding | 0%
BASE BID — MAJOR SCOPE ITEMS
Standing-seam roof panels (MBCI PBR per spec / RFI 23) |  | √
5/8" Dens Glass sheathing at eaves (per RFI 25) |  | ?
Underlayment |  | √
Fascia panels |  | √
Soffit panels |  | √
Ridge / hip caps |  | √
Flashings, closures, drip edge |  | √
Gutters / downspouts (if any) |  | ?
Snow guards (if specified) |  | ?
Trim / accessories |  | √
Manufacturer warranty |  | ?
Color / finish per spec |  | ?
Substrate coord w/ BP 033 |  | ?
BREAKOUTS
Roof only |  | ?
Fascia / soffit |  | ?
ALTERNATES
Corner Guards (likely BP 060/074 scope, not 045) |  | +$0
KEY NOTES & SCOPE GAPS
• SOLE BIDDER. Foursquare (LATE) — non-responsive.
• Bond shows 0.0% in BC — verify actual rate.
• Per RFI 23, metal roofing spec (PBR) takes precedence over plans (Berridge Cee-lock).
• Per RFI 25, sheathing at eaves = 5/8" Dens Glass (no wood).
CORE PRE-AWARD RECOMMENDATION
Sole bidder — validate $49,700 against CORE historical $/SF and verify bond rate.

## BP061
BP #061 — Metal Stud Framing, Drywall & Painting (incl. FRP)
Interior metal stud framing, drywall, painting, FRP at concessions; furring at exterior CMU (per RFI 26).
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Division 09 | Jetstream Construction | M & H Building Specialties
BASE BID (as submitted) | BC Form §Base | 180942 | 257848 | 275259
P&P Bond Rate | Form §Bonding | 1% | 1% | 1.44%
BASE BID — MAJOR SCOPE ITEMS
Metal stud framing — interior walls |  | √ | √ | √
Metal hat channels (vertical) at ext. CMU (per RFI 26) |  | ? | ? | ?
Drywall — 5/8" Type X |  | √ | √ | √
Tape / texture / level 4 finish |  | √ | √ | √
Painting — interior |  | √ | √ | √
Painting — exterior CMU coordination |  | ? | ? | ?
FRP at kitchen / wet walls |  | ? | ? | √
Insulation at metal stud walls (BP 044) |  | ? | ? | ?
Corner beads / trim |  | √ | √ | √
Caulking / sealants (BP 040 interface) |  | ? | ? | ?
Access panels |  | ? | ? | ?
Field repairs / touch-up |  | √ | √ | √
BREAKOUTS
Framing / drywall only |  | ? | ? | ?
Painting only |  | ? | ? | ?
ALTERNATES
Alt 060.01 — DEDUCT Combine w/ BP #062 ACT |  | O | O | noted but unparsed
Alt 060.02 — ADD Corner Guards |  | O | O | O
Alt 060.03 — ADD Wall & Door Protection (10 26 00) |  | O | O | O
KEY NOTES & SCOPE GAPS
• Division 09 — no Form or backup submitted; responsiveness risk.
• M & H most complete submission.
• All three missed Alts 060.02 and 060.03; M&H partially addressed 060.01.
• Per RFI 26 — exterior CMU walls get GYP BD over 1.5" metal hat channels — confirm scope.
CORE PRE-AWARD RECOMMENDATION
M & H most scope-complete; verify Division 09 Form + backup before considering.

## BP094
BP #094 — Bleachers & Press Box (Supply + Install)
Grandstands w/ walking platform, stairs, ADA ramp, press box. Bleacher under-fencing 6'H by BP 023 per RFI 11.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | California Bleachers (NATA)
BASE BID (as submitted) | BC Form §Base | 395379
P&P Bond Rate | Form §Bonding | 0%
BASE BID — MAJOR SCOPE ITEMS
Bleacher frame + seating supply |  | √
Walking platform integral to bleacher |  | √
Stairs / aisles |  | √
ADA ramp + handrails |  | √
Press box structure |  | √
Bleacher fencing TOP (per RFI 11) |  | √
Bleacher fencing BELOW (by BP 023, RFI 11) |  | —
Anchoring to foundation (BP 030) |  | ?
Engineering / shop drawings |  | √
Painting / finishing |  | √
Install / assembly |  | +$48,000 voluntary
Erection equipment |  | ?
Apex height for under-fence sizing (RFI 19) |  | ?
BREAKOUTS
Supply only |  | √ ($395K)
Install only |  | +$48K voluntary
ALTERNATES
Alt 094.01 — ADD Scoreboards |  | ?
Alt 094.02 — ADD Prefab Ticket Booth |  | ?
KEY NOTES & SCOPE GAPS
• SOLE BIDDER. Validate against historical $/seat.
• Bond 0.0% — likely BC parse; supply-only typical.
• Confirm install scope $48K covers full install (anchoring, ADA fitting).
• RFI 19 — apex height needed for bleacher under-fencing — coordinate with BP 023.
CORE PRE-AWARD RECOMMENDATION
Sole bidder — validate $/seat, confirm install scope, get scoreboard + ticket booth alts priced.

## BP098
BP #098 — Plumbing Systems
Concessions plumbing rough-in + fixtures; tie-in to BP 008 wet utilities 5' outside building.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Bombard Mechanical | JW McClenahan Co. | U.S. Mechanical | Universal Plumbing & Heating
BASE BID (as submitted) | BC Form §Base | 390755 | 515000 | 383000 | 375000
P&P Bond Rate | Form §Bonding | 0.6% | 0.9% | 1.12% | 1%
BASE BID — MAJOR SCOPE ITEMS
Domestic water rough-in (Cu / PEX) |  | √ | √ | √ | √
Sanitary DWV (PVC / cast iron) |  | √ | √ | √ | √
Vent piping |  | √ | √ | √ | √
Plumbing fixtures (toilets, urinals, lavs) |  | √ | √ | √ | √
Water heater |  | √ | √ | √ | √
Hose bibs (interior + exterior) |  | ? | ? | ? | ?
Floor drains + funnel drains (kitchen) |  | √ | √ | √ | √
Backflow preventer |  | √ | √ | √ | √
Final tie-in to BP 008 (5' from bldg) |  | ? | ? | ? | ?
Gas piping (kitchen, propane) |  | ? | ? | ? | ?
Testing / disinfection |  | √ | √ | √ | √
Permits & inspections |  | ? | ? | ? | ?
Insulation on hot water piping |  | ? | ? | ? | ?
Fixture trim per spec |  | ? | ? | ? | ?
As-builts |  | ? | ? | ? | ?
BREAKOUTS
Rough-in only |  | ? | ? | ? | ?
Fixtures |  | ? | ? | ? | ?
Gas piping |  | ? | ? | ? | ?
ALTERNATES
Alt 098.01-A — Demo Wet Util at ES |  | +$57,670 | +$239,500 | +$15,000 (cut & cap only) | +$20,000
Alt 098.01-B — New Propane Tank at ES |  | +$34,350 | +$65,000 | +$93,000 | +$15,000
Alt 098.02 — Caliche Unit Rate ($/CY) |  | O | O | O | O
KEY NOTES & SCOPE GAPS
• Bombard front-runner on alt clarity.
• Demo Wet Util alt ranges $15K (cut-and-cap) to $239K (full removal) — major scope basis variance.
• All four missed Alt 098.02 Caliche unit rate.
• Universal & Bombard bond rates may be parse artifacts (0.01% / 0.6%) — verify.
• Combined BP 098 + 100 opportunity w/ Bombard or US Mech.
CORE PRE-AWARD RECOMMENDATION
Bombard front-runner; reconcile Alt 098.01-A scope basis across all bidders.

## BP100
BP #100 — HVAC & Building Controls Systems (incl. T&B)
RTUs, ductwork, controls, T&B at concessions building; kitchen exhaust if any.
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Bombard Mechanical | Sunrise Air Systems | U.S. Mechanical
BASE BID (as submitted) | BC Form §Base | 321320 | 285228 | 241300
P&P Bond Rate | Form §Bonding | 0.6% | 2.5% | 1.12%
BASE BID — MAJOR SCOPE ITEMS
RTUs / package units |  | √ | √ | √
Supply ductwork |  | √ | √ | √
Return / exhaust ductwork |  | √ | √ | √
Kitchen hood ventilation (if any) |  | ? | ? | ?
Exhaust fans (restroom, kitchen) |  | √ | √ | √
Refrigerant piping |  | ? | ? | ?
Duct insulation |  | √ | √ | √
Diffusers / grilles / registers |  | √ | √ | √
Controls / BAS |  | ? | ? | ?
T&B (per NRP — included in BP 100) |  | ? | ? | ?
Startup / commissioning |  | ? | ? | ?
Electrical power (BP 103 interface) |  | — | — | —
Permits & inspections |  | ? | ? | ?
As-builts |  | ? | ? | ?
BREAKOUTS
Equipment supply |  | ? | ? | ?
Ductwork / install |  | ? | ? | ?
Controls / T&B |  | ? | ? | ?
ALTERNATES
Alt 100.01 — Evac Split Sys Refrigerant at ES |  | +$6,500 | +$3,500 | +$7,500
Alt 100.02 — Caliche Unit Rate ($/CY) |  | O | O | O
Alt 100.03 — DEDUCT Combine w/ BP #098 |  | O | — | O
KEY NOTES & SCOPE GAPS
• US Mech lowest base + also bid BP 098 (combined opportunity).
• Bombard 0.6% bond — verify.
• All three missed Alt 100.02 (Caliche) and Alt 100.03 (combine deduct).
• T&B inclusion needs explicit confirmation — NRP put T&B under BP 100.
CORE PRE-AWARD RECOMMENDATION
Evaluate U.S. Mechanical combined BP 098+100 award; push Alt 100.03 deduct in descope.

## BP103
BP #103 — Electrical & Low Voltage Systems (incl. Sports Field Lighting)
Bldg electrical, branch wiring, panels, transformer tie-back, sports field lighting (Musco), LV, fire alarm (per RFI 4).
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Conti LLC | JW Electric | Kill A Watt LLC | Quantum Electric | Wheeler's Electric
BASE BID (as submitted) | BC Form §Base | 1402936 | 807250 | 2033200 | 937714 | 1286010
P&P Bond Rate | Form §Bonding | 1% | 0% | 3% | 1.7% | 1%
BASE BID — MAJOR SCOPE ITEMS
Concessions branch wiring |  | √ | √ | √ | √ | √
Panels, breakers, distribution |  | √ | √ | √ | √ | √
Service tie-back to existing HS ER/TR |  | ? | ? | ? | ? | ?
Sports field lighting fixtures (Musco) |  | ? | ? | ? | ? | ?
Sports field light pole supply |  | ? | ? | ? | ? | ?
Sports field light pole bases (Alt 103.02) |  | ? | ? | ? | ? | ?
Site / parking lot lighting |  | ? | ? | ? | ? | ?
Concessions kitchen power (RTUs, equipment) |  | √ | √ | √ | √ | √
Site power for scoreboard |  | ? | ? | ? | ? | ?
Site power for ticket booth |  | ? | ? | ? | ? | ?
Bleacher / press box power |  | ? | ? | ? | ? | ?
Fire alarm (per RFI 4 — tie to existing FAP) |  | ? | ? | ? | ? | ?
Low-voltage data / telecom |  | ? | ? | ? | ? | ?
Low-voltage A/V salvage / reinstall |  | ? | ? | ? | ? | ?
Grounding / bonding |  | √ | √ | √ | √ | √
Testing / commissioning |  | ? | ? | ? | ? | ?
Permits & inspections |  | ? | ? | ? | ? | ?
Existing one-line / panel sched verified |  | ? | ? | ? | ? | ?
BREAKOUTS
Building electrical |  | ? | ? | ? | ? | ?
Sports field lighting |  | ? | ? | ? | ? | ?
Site lighting |  | ? | ? | ? | ? | ?
Low-voltage |  | ? | ? | ? | ? | ?
Fire alarm |  | ? | ? | ? | ? | ?
ALTERNATES
Alt 103.01 — Electrical Demo at ES |  | +$35,000 | +$32,400 | +$200,000 | +$41,564 | +$34,200
Alt 103.02 — Light Pole Bases (sports lights) |  | O | O | O | O | O
Alt 103.03 — Caliche Unit Rate ($/CY) |  | O | O | O | O | O
RGB lights for football field (voluntary) |  | — | — | +$7,000 | — | —
KEY NOTES & SCOPE GAPS
• JW Electric — extreme low base ($807K) + 0% bond = HIGH responsiveness risk.
• Kill A Watt — $600K+ above next-highest; ES demo alt $200K vs $32-42K others.
• All five missed Alt 103.02 (Light Pole Bases) and Alt 103.03 (Caliche).
• Musco is supplying fixtures (footing info on file) — coordinate w/ awarded sub.
• Per RFI 4 — Fire alarm IS required (tie to existing HS FAP per E3-00).
CORE PRE-AWARD RECOMMENDATION
Quantum Electric — best balance of price + responsiveness. Investigate JW Electric scope before relying on its $807K.

## BP109
BP #109 — Prefabricated Ticket Booth (Supply)
Pre-fabricated ticket booth supply. Install by BP 094 or GC. Final size TBD (4'x6' or 6'x8').
Legend: √ = INCLUDED ¦ O = MISSING / EXCLUDED ¦ ? = NEEDS CLARIFICATION ¦ + = ADD value ¦ − = DEDUCT value ¦ √+ = SCOPE DUPLICATED
Major Scope Item | Notes / SOW Ref | Guardian Booth (6'x8') | Par-Kut International | Porta-King
BASE BID (as submitted) | BC Form §Base | 74763 | 21635 | 17019
P&P Bond Rate | Form §Bonding | 3% | 2% | 0%
BASE BID — MAJOR SCOPE ITEMS
Ticket booth structure (size TBD) |  | √ (6'x8') | √ | √
NV State certified structure |  | √ | ? | ?
PE-stamped structural calcs & drawings |  | √ | ? | √
Windows / pass-through opening |  | √ | √ | √
Door + hardware |  | √ | √ | √
Electrical rough-in |  | ? | ? | ?
Interior lighting |  | ? | ? | ?
HVAC (split / wall unit) |  | ? | ? | ?
Interior finishes |  | √ | √ | √
Exterior finish / color |  | √ | √ | √
Freight to Tonopah |  | √ | ? | √
Foundation / install (by GC/BP 094) |  | — | — | —
Lead time / production schedule |  | ? | ? | ?
BREAKOUTS
4'x6' size |  | √ (Quote #57653) | ? | ?
6'x8' size |  | √ ($74,763) | ? | ?
ALTERNATES
N/A — Supply only |  | — | — | —
KEY NOTES & SCOPE GAPS
• Porta-King lowest at $17K. Guardian most documentation-complete.
• Par-Kut $21K — confirm NV cert, PE-stamped drawings, freight.
• Guardian 3% bond is high for supply.
• Final size selection drives award.
CORE PRE-AWARD RECOMMENDATION
Pending final size selection — Porta-King if cert verified, otherwise Guardian.

## Addenda & Clarifications
ADDENDA & CLARIFICATIONS — SCOPE-RELEVANT ITEMS
Items below are reflected in the per-package scope coverage tabs. Confirm every bidder acknowledges them.
Source | Affected Pkg | Description
Addendum #1 (05.06.26) | Specs | Section 08 71 00 - Door Hardware ADDED to project manual (affects BP 023, BP 056).
Addendum #1 (05.06.26) | Drawings | Drawings C1, GD, G0-00, LS1-10, A1-20 — modified (cloud-tagged). BP 008, 016, 023, 030 affected.
Clarification #1 RFI 1 | BP 008 | No paving at parking area or driveway — graded earth only. Only AC paving is running track per detail J/GD.
Clarification #1 RFI 2 / 6 | BP 008 / BP 021 | Track AC = 4" Type II. Detail L on GD is asphalt (not concrete).
Clarification #1 RFI 4 | BP 103 | Fire Alarm REQUIRED per code — tie to existing HS FAP (per Sheet E3-00).
Clarification #1 RFI 5 | BP 089 | Scoreboard BOD = FB-2021 (FB-2022 discontinued).
Clarification #1 RFI 8 | BP 008 | No slope stabilization required.
Clarification #1 RFI 9 | BP 023 | Propane Tank Enclosure (Alt 023.01-C) = assume 150 LF, 6'H + 1 pair 3'-0" access gates.
Clarification #1 RFI 10 | BP 023 / BP 008 | Salvage existing fencing — reuse fabric, hardware, and posts (reinstall). Demo by SOW 008.
Clarification #1 RFI 11 | BP 023 / BP 094 | Fencing TOP of bleachers by BP 094. Fencing BELOW bleachers (under) by BP 023, 6'H.
Clarification #1 RFI 13 | BP 023 | Chain link post footings — 6" below post bottom.
Clarification #1 RFI 14 | BP 008 / BP 022 | Finished subgrade (compacted earth) and gravel subbase by BP 008. Geotextile + leveling sand + turf system by BP 022.
Clarification #1 RFI 15 | BP 008 / BP 022 / BP 030 | Turf scope restructured: Base = turf above shock pad. BP 022 to provide DEDUCT alts for: Geo Liner, Leveling Sand, Field Drainage, Header Board. BP 008 to provide ADDITIVE alts for first three. BP 030 to provide additive alt for Header Board.
Clarification #1 RFI 16 | BP 002 | Buildings to be abated = Bldgs #3-7 (was 3-6 in SOW).
Clarification #1 RFI 17 | BP 023 | Temp fencing = 2,800 LF at HS + 2,300 LF at ES.
Clarification #1 RFI 18 | BP 023 | Gate locking device per Section 08 71 00 (added by Add #1) + Section 32 31 13 §2.04.
Clarification #1 RFI 19 | BP 094 | Apex height of bleachers — contractor to coordinate with mfr (needed for under-fencing height per RFI 11).
Clarification #1 RFI 20 | BP 023 | Existing HS fencing replaced entirely (base bid). Deduct alt per RFI 10.
Clarification #1 RFI 22 | BP 023 | A1-20 takes precedence on post sizes (overrides spec 32 31 13).
Clarification #1 RFI 23 | BP 045 | Metal roofing spec (MBCI PBR panel) takes precedence over plans (Berridge Cee-lock).
Clarification #1 RFI 24 | BP 021 | Track surfacing — install per mfr spec, MINIMUM 2 coats structural spray coating.
Clarification #1 RFI 25 | BP 045 | Sheathing at eaves = 5/8" Dens Glass (no wood).
Clarification #1 RFI 26 | BP 031 / BP 061 | All exterior CMU walls + restroom vestibule walls: CMU + 2" rigid insulation + fluid-applied AWB + 1.5" vertical hat channels + GYP BD. Knit takes no exception to standard Z-fur w/ rigid as alternative.
Clarification #2 (05.07.26) | ALL — MAJOR | PREVAILING WAGE CHANGED — Project subject to CL-2026-100 (Clark County rates, NOT Southern Nevada Rural Region as originally stated). All bids must use CURRENT Clark Co. wage rates per NV OLC.
Clarification #2 | ALL | SB 82 Apprenticeship — project is a VERTICAL Construction Project.