## cover sheet
Attachment A Review Log
NCSD - Tonopah High School Sports Field Replacement
26-01-019
Approved By | Approval Stamp |  | Reviewed By | Reviewed Stamp
Project Director |  |  | Project Manager
General Superintendent |  |  | Superintendent
Tim Roley or Matt Wade (if over $5M) |  |  | Assistant PM (if applicable)
Final Session; add Invitees: Anne Tall, Erin Hicks, Kathleen Hamilton, Liz Pippett, Inger Pippett
Subcontractor: |  | New-Com, Inc. (TAB Contractors and MMC, Inc.)
Anticipated Material Procurement Date: |  | CONFIRM
Anticipated Start Date: |  | CONFIRM
*Phase Code | 02-1000-10000 |  | Dollar Amount | 1741321
*Only one Phase Code Per Subcontractor/Vendor per Tim Roley
TOTAL (should equal contract total)

## contract amount summary
How we got to the contract amount — RFP-008 — New-Com, Inc. (TAB Contractors and MMC, Inc.)
Reconciled to GMP R2 leveling sheet tab '8' (Site Demo, Earthwork, Paving & Wet Utilities). The leveling total is SUM of the priced column; values marked with an asterisk on that sheet are options and do not count toward it.
Base Bid — TAB proposal 05.12.26, restated 05.22.26 | 1924851
Deduct: delete Type II and geofabric from turf field | -150000
Deduct: delete slot / trench drains at track | -125000
Add: additional 8" perforated field drain, south end of field (210 LF) | 30000
Deduct: Accepted VE #10 — leave access road as-is (incl. relocation of 2,100 CY to stockpile) | -16750
Add: D-10 dozer for hard dig, 1 month (saves 2 weeks) | 70000
Add: trencher for storm drain | 18720
Deduct: Accepted VE #9 — RCP flared end section in lieu of headwall | -10500
CONTRACT TOTAL | 1741321

## list (hidden)
Roger Baum
Merv Giles
Matt Buckhannon
Jim Jacobs