Subcontractor:  NDX

Scopes:  Abatement & Building Wrecking

Project:  NCSD Tonopah HS Field Replacement

Date:  5/14/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn Duranleau | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo Gomez | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Daryl Hanks | NDX | Estimator |  |
| 8. | Gio | NDX | Estimator |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Clarify asphalt section cut 4” of asphalt over 4” of type 2

    - Excludes demo of propain tank (Propain company to demo)

    - Excluded runway mix for the shot put area

    - Excluded sand on the long jump pit

    - Clarify using PG76 (Oil, based on previous project, more expensive)

    - 3/8 mix for track

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

    - Elementary building 4 has 2 floors of concrete walls and stairs

  - Inclusions or assumptions to cover grey areas in the scope

    - Haul off to Beatty

    - Local landfill only allows for 15tons a day

    - No spoils onsite

    - Includes calichie at below current grade 5 ½ ft on south, 2 ½ ft on the north under item #9

    - Add asphalt 4” on 4” to half moon ends.

    - Add asphalt 4” on 4” to ambulance parking stall east end

    - Adds grading the north end lot to be cut to drain

    - Assume basic geoliner due to no product number

    - Include control/inspection to SWPPP while on site

    - Includes placement of type 2 at the sidewalk (24k) and building pad (2.9k)

- Alternates

  - Demo of the existing elementary school

  - Caliche unit rate in areas not specified in Geotech report

  - Geoliner and sand – separate type 2 from native

  - Included 4” of drain rock under turf – Need design team clarification

  - Abatement by Action Solutions 2nd tier sub

  - Dust palliative to all disturbed areas

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Balancing |  | 30 days |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Price for onsite spoils for grading and utilities

- Breakout geo-liner and sand alternate 8.04

- Add herbicide for asphalt (special license required)