Subcontractor:  Northstar Contracting Group

Scopes:  Abatement & Building Wrecking

Project:  NCSD Tonopah HS Sports Field Replacement

Date:

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Fernando Cerda | Northstar | Estimator |  |
| 8. |  |  |  |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Gas, water, and electrical cap by others

    - Excludes clearance sampling

    - Excludes salvage of copper and feeders

    - Excludes cost escalation for snow

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

    - Two abatement reports were provided, priced the one with more quantities.

    - Abatement on 5 buildings

    - Slab remains on the demo of 5 buildings

    - Hire trucks for dumping (from Las Vegas)

    - Includes Nye County and zone rates

    - Includes Tectura in base bid

    - To include third-party monitoring

    - Buildings 1 and 2 will still be occupied during abatement

    - Assumes CMU walls for building demo

    - Hand demo at canopy/building

    - Includes the demo of the feeders of the elementary school

    - Assumes no lead paint, if present, no issues removing.

    - Includes capsul for abatement depending on the amount.

    - Includes living costs.

    - Includes saw cutting, digging, and capping 24” below grade of utilities.

    - Northstar confirmed haul-off of all demo material is included.  – JG 5/29/26

    - Northstar confirm deduct of 37,178 for abatement. – JG 5/29/26

- Alternates

  - The report does not mention the transit pipe. Alternate 1 is for dispole if it exists.

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

  - Includes a demo permit and abatement of air quality

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Abatement |  | 1 month |  |  |
| Demo |  | 1 month |  | To work during winter (Snow) |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Add price for a spray dust palliated (20ft around the buildings) permit

  - Send specs of dust palliated

- Verify landfill haul-off location

- Provide updated quantities for abatement

- Breakout price for abatement for buildings 1 and 2

- Provide acceptance of 4-10s.

- Provide an alternate for building 4 demo per AD1.16