Subcontractor:  Quantum Electric

Scopes:  Electrical Systems

Project:  Tonopah HS Field Replacement

Date:  5/20/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Joe Curry | Quantum Electric | Project Manager |  |
| 8. |  |  |  |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Excluded footings for light poles

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

    - Included salvage, storage and reinstall of existing equipment

    - Includes safe off of existing power

    - Includes new transformer and Musco lighting control

    - Includes hard dig rate

    - Assume only precast and install for light poles

    - Includes all trenching for conduit runs

      - Prioritize trenching on the field

    - Assumed onsite spoils

    - Crane to be provided from Elko

    - Includes all power, lighting, low voltage, mechanical hook-up, owner furnished cameras and speakers

    - Assumes conduit

    - Includes coordination for CMU penetration

    - Includes temp power, lighting and spider boxes

    - Assumes speakers are in good conditions

    - CORE to advise if scoreboards controls are wireless

    - Excludes patch-backs and paint for existing building tie-in

    - Includes caulking

    - Includes mule tape

    - Assume press box is pre-built and furnished

    - Assume transformer and panel for press box to be provided by Quantum

    - Includes pulling feeders and cutting them below grade

- Alternates

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| Musco Lights |  | 8 weeks |  |  |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Electrical | 2-3 guys |  |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Provide pricing for all hard dig.

- Provide concrete for light poles

- Confirm dust control is included

- Provide breakout for press box receptacles and lighting

- Provide duration for hard dig