Subcontractor:  Sunrise Air Systems Inc.

Scopes:  HVAC Systems

Project:  Tonopah HS Field Replacement

Date:  5/18/26

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Micheal Ruesch | CORE Construction | MEP Preconstruction |  |
| 8. | Jeff Ingleberger | Sunrise Air | Project Manager |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Did not include safe off of existing concessions building HVAC (none indicated on drawings)

  - Factory mounted disconnects are not included (not needed for equipment specified)

  - Filters are included

  - Included VRF shop drawings and engineering of piping sizes

  - Included standalone controls only, BMS system is not included

  - T-stat conduit not included – stated that he can cover this (box and conduit stub to above ceiling only) can cover if duct detectors are not required

  - Included 5 duct detectors, but may not be required ($1,700 worth)

  - Control of exhaust fans is by line voltage

  - Included Test and Balancing

  - Assumes no formal Cx. Included manufacturer startup

  - Seismic engineering – don’t believe is required. Will include stamped exemption letter

  - Include smoke/fire sealants for own scope of work

  - Access panels (supply only) in hard lids for access to own work

- Add Alternate #1

  - Figured two techs for one day.

- Included southern rural wage rates provided with RFP

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

SCHEDULE

- Project Milestones

  - NTP Showing end of July

  - Start for this scope: May 2027

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| EF’s |  | 3 weeks |  |  |
| VRF | 2 weeks | In stock |  |  |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| MEP OH Rough |  | 2 weeks |  |  |
| MEP Trim |  | Couple days |  |  |
| Startup |  | 2 days |  |  |
| Evac at existing |  | 2 days |  |  |

SAFETY

- CORE PPE Requirements Hard hats strapped required

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract Covered

- Insurance double check

- Textura included

- LCP Tracker

- Apprentice Utilization Requirements good with this