Subcontractor:  New-Com Inc (TAB)

Scopes:  Site Demo, Earthwork, Paving, Wet Utilities, and Site Signage

Project:  Tonopah Field Replacement

Date:  5/19/2026

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Shane Haycock | TAB | Estimator |  |
| 8. | Angel Selinas | TAB | Estimator |  |
| 9. | Travis Roder | TAB | BD |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Exclusions or clarifications to the scope

    - Excluded caliche

    - Excludes leveling sand

    - Excludes 3/8”x1/2” fractured rock

    - Excludes slope stabilization

    - Assume the dust palliative is not included

    - Excludes track and field signage

    - Excludes DG at shot put and discus area

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

    - Includes sweal on east elevation

    - Assume cut on the new parking lot

    - Assume use trucks for hauling off

      - Will dump holes on SPWD land

      - Dump trash in the local landfill

    - Assume 4” type 2 base at turf.

    - Assume 6” aggregate base and 4” of asphalt.

    - Assume the slot drain on half moons

    - Assume 8” slot drain at 3ft deep

    - Includes head wall and rip rap

    - Includes concessions

    - Assume 18” cut for slot drain.

    - Assume 1ft cut for concrete curb

    - Assume 6” of type 2 at the building pad concrete

- Alternates

  - Civil demo of existing elementary school

  - Includes caliche unit rate of $40/CY

    - Assume D4/5 dozer

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP

  - Early Start for this scope:

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Rough Grade |  | 30 days |  |  |

SAFETY

- CORE PPE Requirements

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- 501c(3)

- Nevada 1st requirements

- Skilled and Trained Workforce Requirements

- Apprentice Utilization Requirements

HOMEWORK

- Provide pricing for D10 dozer.

- Provide deduction on clean spoil to remain on-site.

- Confirm with the local landfill that it will receive all trash quantities.

- Provide a breakout for the base (type 2 and geofabric) at the turf field.

- Clarify the type of paving and thickness for the track.

  - CORE to send specs from track trade partner

- Provide a breakout for the trench drain

- Provide cost for the added 8” perf to connect to the storm drain.

- Provide breakout for type 2 at building pad and concrete paving