Subcontractor:  U.S. Mechanical

Scopes:  HVAC Systems & Plumbing Systems

Project:  Tonopah HS Field Replacement

Date:  5/18/26

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager | Not present |
| 2. | Keith LaRue | CORE Construction | Superintendent | Not present |
| 3. | Dawn | CORE Construction | Pre-Con Manager | Not present |
| 4. | Jairo | CORE Construction | Project Engineer | Not present |
| 5. | Avery Hacker | CORE Construction | Project Director | Present |
| 6. | Derek Rosse | CORE Construction | General Super | Present |
| 7. | Michael Ruesch | CORE Construction | MEP | Present |
| 8. | Travis Starley | U.S. Mechanical | Estimator | Present |
| 9. | Justun Bylund | U.S. Mechanical |  | Present |
| 10. |  |  |  |  |

SCOPE

Plumbing:

- Review the Scope Narrative and subcontractors proposal

  - Included safe off, capping, and salvage of 3 compartment sink

  - No permits included

  - Condensate drain piping – included in plumbing scope

    - CORE requests add for insulation on condensate drain piping

  - Plumbing equipment and fixtures are per the schedule in drawings

  - Included layout for CMU sleeves and block outs

  - Joint sealant of penetrations – not include. US to double check and provide add if necessary

  - Seismic engineering and restraints are included

  - Camera of 4” sewer line is included

  - Supply of access doors for own scope is included

  - Excavation spoils: need to double check haul off assumptions

  - Hard dig included? US to check and provide additional cost

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

  - Alternate #1: Included, but only cut and cap above grade. Relook at scope to include sawcut, digging, and capping 2 feet below grade per detail in drawings. Include concrete pourback.

  - Alternate #2: CORE requested additional price for put back of site finishes disturbed by excavation

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

Mechanical:

- Review the Scope Narrative and subcontractors proposal

  - All equipment included is per the schedule

  - Included stand alone controls for VRF system

    - CORE to find out if BMS monitoring will be required or not; will let US know if HW request is required

  - Included conduit and backboxes for t-stats up to accessible ceiling

  - Included seismic engineering and restraints

  - Will include 4 sets of filters total on the project

  - Includes cutting of roof deck for exhaust fans

  - Includes supply of access panels for HVAC scope

  - Test and Balance is included

  - Includes regulators for dampers in hard lids

  - US to provide an add for a low-ambient kit for outside unit

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

  - Alternate #1: refrigerant recovery split systems: assumed 1 day for this scope

  - Alternate #2: packaged deduct (plumbing and HVAC combined) : $10,000 savings

- Value Engineering

- Weather Protection

- Hoisting

- Permits none included

- Testing

SCHEDULE

- Project Milestones

  - NTP end of July

  - Start for this scope: On site start around Thanksgiving

  - Other milestones relating to this scope

  - Substantial Completion

  - Plan on 4-10s – US good with this

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| VRF System | 4 weeks | 8-10 weeks |  |  |
| Exhaust Fans |  | 8-10 weeks |  |  |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| Plumbing UG | 2-3 guys | 1 week |  |  |
| Plumbing & HVAC Rough | 3-4 guys | 4-6 weeks |  |  |
| Plumbing & HVAC Trim | 2-4 guys | 2-3 weeks |  |  |

SAFETY

- CORE PPE Requirements CORE requires type 2 hard hat with strap

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING Discussed and all is covered.

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- Apprentice Utilization Requirements