Subcontractor:  Universal Plumbing & Heating Co.

Scopes: Plumbing Systems

Project:  Tonopah HS Field Replacement

Date:  5/18/26

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Vic Poma | Universal | Vice President |  |
| 8. | Michael Ruesch | CORE Construction | MEP Precon Mgr |  |
| 9. | Dave | Universal |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal Did review RFP scope of work provided

  - For existing concessions safe off, included digging and capping of lines.

  - Included condensate drain piping

    - No insulation, provide add to insulate

  - Included camera of 4” lines and large

  - Seismic only needed on water heater

  - Sealants included for own penetrations

  - Included hard dig for excavation if necessary

- Add Alternate #1

  - Included capping existing utilities 2 feet deep per drawings

- Add Alternate #2

  - Included supply and install of propane tank (size is tbd, Universal to find out what was carried)

  - Double check what routing was included by the 2nd tier

  - Confirm if concrete pad is included or not

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

- Value Engineering

- Mock Ups

- Weather Protection

- Hoisting

- Permits

- Testing

SCHEDULE

- Project Milestones

  - NTP Estimated end of July - confirmed

  - Start for this scope: Next March - confirmed

  - Discussed 4-10 scheduled. Confirmed

  - Substantial Completion

- Material Procurement

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |

- Durations

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
| UG Plumbing | 2-3 guys | 1 week |  |  |
| OH & In Wall Plumbing | 2-3 guys | 3 weeks |  |  |
| Plumbing Trim | 2-3 guys | 1 week |  |  |

SAFETY

- CORE PPE Requirements Confirmed strapped hard hats included

- DAHA

- Safety manual and SDS manuals on site

  - Use Worldwide Safety as 3rd safety coordinator

- Logistical challenges

  - Site Logistics Plan

  - Staging

- Project specific background checks

- Project specific safety requirements

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- Apprentice Utilization Requirements

  - Covered

HOMEWORK

- Provide add for insulation on condensate drain piping

- Review Add Alternate #2 scope and assumptions included