Subcontractor:  Wheeler’s Electric, Inc

Scopes:  Electrical Systems

Project:  Tonopah HS Field Replacement

Date:  5/18/26

Attendees:

|  | Print Name | Company | Role | Sign-In |
| --- | --- | --- | --- | --- |
| 1. | Jon Cox | CORE Construction | Project Manager |  |
| 2. | Keith LaRue | CORE Construction | Superintendent |  |
| 3. | Dawn | CORE Construction | Pre-Con Manager |  |
| 4. | Jairo | CORE Construction | Project Engineer |  |
| 5. | Avery Hacker | CORE Construction | Project Director |  |
| 6. | Derek Rosse | CORE Construction | General Super |  |
| 7. | Micheal Ruesch | CORE Construction | MEP |  |
| 8. | Taylor Leavitt | Wheelers | Estimator |  |
| 9. |  |  |  |  |
| 10. |  |  |  |  |

SCOPE

- Review the Scope Narrative and subcontractors proposal

  - Includes removal of existing field lighting and scoreboard, excluding haul off (by others)

  - Will provide connex storage for salvaged equipment to be re-used

  - For work in existing high school, drywall and paint repairs are excluded

  - Hard dig not figured for any excavation

    - Wheelers will review and provide unit price for hard dig and expected quantity

  - Included short circuit/arc flash study and coordination

  - Sports Field Lighting

    - Includes precast Musco light pole bases

    - Includes grouting of bases after they are set

  - Temp power: will provide temp power to one connex trailer, two spider boxes, and temp lighting in the building.

  - Fixtures included per the schedule

  - Plywood backboards are included in TR room

  - Included surface mounted conduit and fixtures in press box

  - Fire Alarm is not included (referenced precon RFI)

    - Wheelers to reach out to Teledata for a budget price to add Fire Alarm to the concession building

  - Exclusions or clarifications to the scope

  - Deviations from specifications

  - Deviations from plans or details

- Specific or Unique scope

  - Scope holes from past experience on this type of project

  - Inclusions or assumptions to cover grey areas in the scope

- Alternates

  - Alternate #1: Add $34,200 for electrical demolition at abandoned elementary school

SCHEDULE Discussed 4-10s

- Project Milestones

  - NTP end of July

  - Start for this scope: November for Demo, rest of work will start end of January/early February

  - Other milestones relating to this scope

  - Substantial Completion

- Material Procurement Taylor to review and get back to us

| Material | Submittals/Shops | Lead Time | Fabrication | Notes |
| --- | --- | --- | --- | --- |
| Transformers |  | 8-10 weeks |  |  |
| Musco Lights |  |  |  |  |

- Durations Taylor to review durations and provide feedback

| Activity | Crew Size | Duration | Manhours | Notes |
| --- | --- | --- | --- | --- |
|  | 3-4 |  |  |  |

SAFETY

- CORE PPE Requirements All workers required to have Type II hard hats with strap

- DAHA

- Safety manual and SDS manuals on site

- Logistical challenges

  - Site Logistics Plan

  - Staging

ADMINISTRATIVE/CONTRACTING

- Template Subcontract

- Insurance

- Textura

- LCP Tracker

- Apprentice Utilization Requirements